Improving the availability and use of diverse seed and other planting materials to reduce vulnerability and improve food security for smallholders in vulnerable ecosystems

Final Report LoA 15/039

- Coordinator and staff in the national partner institution

Coordinator: Ximena Cadima Fuentes

Technical team: Rhimer Gonzales (full time), Franz Terrazas (partial time)

Monitoring: general management and technical management of PROINPA

Communication support: Samantha Cabrera

Accounting: Hortensia Trujillo

- Institutions involved in the implementation of the LoA and coordination between them

Fundación PROINPA: Project coordination, implementation of activities and strengthening the dialogue between actors of the seed supply system.

INIAF (National Institute of Agricultural and Forestry Innovation): Agent certifying plots and seed quality, and training of seed producers about seed certification.

Seed producers (farmers associations of two communities: Pico Central and Linde, from Colomi municipality, Cochabamba department): Beneficiaries of the project (equipment, diverse seeds, technical assistance and training).

- Activities carried out under the LoA and their results.

In Bolivia, the project is conducted in Cochabamba, in the municipality of Colomi. Two crops are the target of the project: potato (Solanum tuberosum) in the high area (puna zone), and arracacha (Arracacia xanthorrhiza) in the tropical area.

Output 1. Enhanced capacity and diversification of seed suppliers and other stakeholders to provide local crop genetic diversity planting materials in large enough quantities to minimize risk for smallholders in vulnerable ecosystems

Activity 1.1 Understanding seed systems: actors involved, system’s capacity to provide crop diversity, system’s ability to adapt to changes, farmers’ preferences and choices

Analyze the amount of diversity for selected traits at the beginning of the project and at the end of the project

An analysis of the state of diversity of native potato was performed with families in the communities of Pico Central and Linde using five-cell analysis. We believe that the status of conservation would be more practical considering a broader spectrum of information collection. In this sense, the last months of 2015, farmers representing communities from the three altitudes levels of the puna of Colomi were addressed to assess the state of conservation of native potato diversity, which includes mapping varieties with functional features. GIS tools are been used as complementary tools for this analysis. Final results of this analysis will be presented in technical reports of 2016. See Annex 1, an example of data collection using five-cell analysis, and a map of family plots with potato diversity.

Farmers’ preferences in project sites

During the agricultural season 2014-2015, collection and analysis of information about farmers’ references in terms of seed suppliers and in terms of varieties and seed, and market trends were focused on arracacha. Structured interviews were conducted with producers of the tropical zone of Colomi (Tablas Monte) and the methodology "Fast Market Survey" were applied to arracacha marketers (wholesalers) to identify the main criteria used in obtaining seed (quantity and quality), and selecting varieties that are cultivated and marketed.

- Seed sources, diversity and production destination of arracacha from Colomi

Arracacha producers prefer to use their own seed, but eventually they also buy or rely on their social relationships to obtain new seed. The theme of social relations is very important in the case of obtaining new seed and diversity of arracacha. The main sources are neighbors, relatives, friends, “compadres” (godfather), acquaintances from the same community, and a few farmers are turning to producers of other communities. Arracacha producers say there is very limited availability of seed. The sale is minimal, the producers prefer not to sell seed, in this way they believe to prevent overproduction and oversupply of arracacha in the market.

Arracacha producers in tropical Colomi use of 1-10 qq seed (1 qq = 46 kg), with an average of 5 qq / family, and establish plots of 0.1 to 2 ha, with an average of 0.6 ha / family. These data correspond only to the commercial variety K'ellu. Producers do not consider the surface of the non-commercial varieties, because those are grown in home gardens. The gardens can have 50 to 100 plants per variety and its production is destined for family consumption and as a source of renewal and seed multiplication.

Producers recognize three morphotypes of arracacha (K'ellu, Kulli and Yuraj) which are differentiated mainly by the color of the root, however, within each morphotype, there is variability that is distinguished by the size and color of foliage, shape and secondary color of the roots.

Managing arracacha seed takes place in the same plot. After the harvest of the roots of arracacha, modified stems (corona where the propagules are) remain on the plot, they are covered with plant material thus preserved for up to 6 months or until the new planting.

- Analysis of wholesale market of arracacha in Colomi

Colomi’s fairs take place twice a week (Thursday and Sunday) but arracacha marketing is done only on Thursdays. This market only offers arracacha to eat, not seed. Best selling season of arracacha (K’ellu variety only) takes place in from September to December, when demand of arracacha rises due to higher occurrence of social events such as weddings and graduations taking place in the city of La Paz where 100% of arracacha from Colomi’s fair is destined.

The negotiation for the price in the market is performed at the time of purchase and sale arracacha. The trader makes payment to the producer immediately or occasionally a week later.

According to the results of monitoring prices between August and November 2015, the price for a bag of 50 kg of arracacha (known locally as quintal) vary throughout the year. The last weeks of November, the price tends to increase as supply decreases (Fig. 1).

Figure 1. Weekly monitoring of prices and quantities of arracacha at the Colomi fair (August to November / 2015)

The market of arracacha from Colomi is the only one, so there is no competition for supplying this product in Cochabamba. The community of San Juan de la miel (municipality of Coroico, La Paz) is the main competitor nationally.

Traders coming from La Paz to obtain arracacha in Colomi, just buy the variety K'ellu because it is the favorite in La Paz. When the supply of K'ellu is very low, occasionally traders buy arracacha of white root (Yuraj variety) paying half the price of the arracacha yellow root (K'ellu). According to those traders, yellow arracacha (K’ellu) tolerates better the process of transportation and storage and roots present few problems and deterioration after being washed before transportation to the city of La Paz.

The merchants of La Paz prefer arracacha roots of intermediate size (4-10 cm in diameter and 20-30 cm long), without damage from bumps and not broken. However, they indicated that the last few months, producers are not meeting these requirements, so the price has fallen due to the poor quality of the product offered. This is a reflection of the producers are not being careful during the selection and proper handling of the seed, which is a critical step during the production process of arracacha. There are also other factors contributing to the low quality of the final product, such as poor transport conditions of the roots from the plot of the producer to the market.

Despite the decreased quality of arracacha in Colomi market, it is still evident that there is a weekly demand of 50-200 qq  arracacha (variety K’ellu) by wholesalers from La Paz, so there is a constant demand for seed.

Collect and analyze information of how collective action rules influence seed and information exchange

An analysis was conducted about how organizations of potato seed producers from Colomi work and how its rules affect seed systems in Colomi. For this purpose, the participatory action research methodology was used.

- Influence of local organizations in seed production

Less than 5% of producers from Colomi have access to high quality seed. Eventually, local organizations such as the Municipal Government and some NGOs influence seed production by injecting basic seed of potato varieties. Currently, only PROINPA in the framework of this project is working on the injection of basic seed of different native potatoes.

Potato seed producer organizations strengthened in the years 2013-2015 in the framework of this project have succeeded in opening a local market for quality seed of a number of native potato varieties, achieving influencing the quality of seed available in their communities. However, the results of this effort in terms of volumes may be more evident only in subsequent years.

- Determination of sowing seed potato varieties

Families and productive organizations perform continuous monitoring at Colomi local market, where they observe trends in prices of different varieties of potatoes throughout the year. With this information, producers prioritize those varieties with increased demand.

In terms of cultivated area, commercial varieties (native and improved) are planted in 90% of the land prepared for cultivation of potatoes a year, and only 10% for growing varieties for home consumption. Commercial varieties are planted in areas of 2000-5000 m2, especially in areas where mechanization is possible, while varieties that are only used for their own consumption are planted in plots of 300-500 m2.

Access to different ecological zones (different altitudinal levels) determines the diversity of potato to be cultivated. A sampling carried out in 5 communities, about the diversity of cultivated potato, showed that the greatest diversity of potatoes (native and improved varieties) is in communities that have access to land in the highlands (above 3750 m), where there is the most soil conditions for seed production (Fig. 2).

Low puna (3250–3350 m)

Hillside (3350–3750 m)

High puna (3750–4200 m)

Figure 2. Potato crop diversity in different ecological zones of communities Kanko, Palta Loma, Pico Central, Pisly and Linde, municipality of Colomi.

- Taking collective decisions

Colomi communities are organized into agrarian unions (sindicatos), which regulate internal and external relations of communities. Sindicatos administer justice according to unwritten codes handled by tradition, solve issues of land and roads, conflicts of agricultural and livestock production, and also socio-cultural and political issues.

Productive organizations formed within sindicatos (such as the Linde and Pico Central producers organizations) establish collective performance standards and operation such as the appointment of responsible, use of funds and assets of the group, planting and plant diversity, and rules on the marketing of the production group.

Group decisions are taken only for the activities carried out as a group, but do not influence into family individual actions.

- Influence of local regulations in the seed system

Traders intermediaries have advantages over the local producers. They have access to different potato markets in the country, therefore they are the ones largely define the price and varieties. When seed demand is great, the intermediaries rescue small common potato and sold them as seed without any quality control.

Seed producer organizations that are under development in Colomi not yet have sufficient political and social influence to propose strategies to regulate the production of native potato seed in terms of quality standards and price.

- Internal rules of the seed producers organizations to define the seed management

Planting seed is a decision by the group when the seed is of basic category (high genetic value). Once the basic seed has been multiplied by the group (for one or two growing seasons), it is distributed to producers and members of the seed growers group.

The internal rules may vary according to the group. For example, the Pico Central group has defined the distribution of seed from basic material in three equal parts. One part goes to the individual administration of the producer members of the group, another part goes to seed basket fund of the organization and the last part goes to the administration of the project, who together with the producers define the use and destination of the seed.

Families of farming communities with strong reciprocal relationships and work are more likely to respond to work and joint initiatives, while communities with families with weak community relations are more individualistic.

The amount of seed to produce is defined individually depending on the availability of suitable plots for this purpose (access to different ecological zones, healthy soils).

The families of the communities Linde / Pisly have soils with no steep slopes (5-10%), so farming can be machined. Every family has the potential to produce an average of 10 tons of seed (200 bags of 50 kg each) and at least 20 tons of potato consumption (table potato) (200 bags of 100 kg each). While in Pico Central community, which is a hillside area with steep slopes (30-60%), the average seed production capacity from each family is 3 tons (60 bags of 50 Kg each) and 7 tons potato consumption (70 bags of 100 kg each).

Case studies on how different seed systems have evolved and adapted to changes and/or responded to crisis situations, including dramatic climate variations

In previous reports, it was shown how planting dates were modified and adapted to climate variations in Colomi.

Now additional information is presented on local indicators to manage the climate. Information retrieval on climate indicators was conducted through workshops and meetings with potato producers in the communities of Pico Central and Linde.

- Zoo-indicators

The behavior of wild animals is a major source of information in making decisions about crops in the high Andes. The most commonly used indicators are related to the behavior of rainfall which is considered as the main climatic phenomenon that determines agricultural productivity, especially potatoes.

Atuj (fox)

Fox observations on August 1 and September 14 (religious feast of the Lord of Exaltation) relate to the prediction of annual rainfall.

The observation is to hear the howling of foxes; if it is continuous and clear, then it is interpreted as predicting a good year for crops with an adequate distribution of annual rainfall, while if the howl is distorted and discontinuous (as it is jamming), then it is interpreted that the rains will be scarce.

This observation is critical and influence seed systems because is the basis for determining the most appropriate planting time (early, middle or late) and the production area (in flat areas or on slopes) more convenient for annual main planting.

Behavior of local birds

Observing the construction of some birds’ nests in the potato field also predicts the behavior of the rains. This observation is between the months of November to January. If the birds build their nests in the potato cultivation, preferably over the groove, farmers relate this behavior with the presence of abundant rain; whereas if these nests are located in the deep part of the groove shortage or little rain is expected.

- Phyto-indicators

Muña (Minthostachys sp.)

Muña observing is in the month of September to October, at the beginning of the planting season. When muña flowers abundantly, it is a sign of a good year for crops, which means good distribution of rainfall, whereas when flowering is scarce, it will be little rain in the year that will not accompany the development of the crop.

Sank´ia (Echinopsis sp.)

The Sank’ayu or Sank'ia is a cactus widespread in the Andean region of the country; it is used as the main indicator for the cultivation of potatoes and other Andean tubers, observing the amount of fruits in the months of July to September. If the fruits are abundant, the potato crop will have poor performance, whereas when the Sank'ia has little fruit, then the potato crop will have good performance.

Other producers use flowers as indicators, this observation is usually done in the month of August. In this case it is also a sign of good year (mainly for growing potatoes) when Sank'ia bloom is abundant, indicating that the potato harvest will be plentiful, whereas if the bloom is weak or is destroyed by the cold winter potato production will be limited.

- Using the information of climate indicators in potato cultivation to determine early or delay plantings

Some potato farmers in the region Colomi venture to predict the behavior of rains next year from observing weather conditions the current year and say: "If this year is dry, with little presence of rain, the following will be wetter so let’s sow earlier". This situation has influenced the planting date and harvesting season. Colomi farmers use additional strategies such as planting at different times in order to reduce risks.

The observation of changes in rainfall patterns has made farmers alter the agricultural calendar by the advancement of the planting season in some regions and delays waiting for the rains in others. This is explained in detail in previous report.

Many of the observations of zoo-indicators and phyto-climatic indicators are obsolete, have been forgotten or no longer transmitted, but some of this knowledge are still commonly used by both young people and adults, and have influence in seed systems, particularly in the definition of planting season and amount of seed to invest according to the expected good or bad year.

Activity 1.2 Strengthening linkages between diversity of actors in the seed system

Test out mechanisms/methodologies to enhance and maintain communication between actors

Meetings were promoted between the national authority on seed (INIAF) and seed producers from Colomi in order to enhance communication between them.

Results of this process include for example that INIAF already recognizes Pico Central and Linde seed producers of native potato as part of the regional system of seed potato suppliers, and these producers are called by INIAF for official meetings and routine activities (see Annex 2).

In order to make visible the work of seed producers groups, in previous years a radiocast (in Quechua) about potato seed producers from the communities Linde and Pico Central was continuously transmitted through the local radio in Colomi.

In 2015 the local company of Tv Radio Nogales Record developed a television spot with the support of the project. This audiovisual product has been developed in Quechua, using photographs (provided by PROINPA) showing the different organizational processes, soil characteristics and communities, monitoring and controls internal and external quality as well as the stages of harvesting, selection, storage, promotion and sale. Photographic video content (script) is in Annex 3.

Place information on quality seed suppliers, seed prices and sources of foundation seeds on a public website (hosted by the Ministry of Agriculture or other Ministries where possible). (INIAF website)

Meetings with INIAF were promoted to establish the information required to include seed producers of Pico central and Linde in the INIAF official register of seed suppliers. The INIAF committed that information on production areas, varieties available and contact producer organizations of native potato seed Pico Central and Linde-Pisly, will publish in the INIAF annual report for seed suppliers during the cropping season 2015-2016.

Test mechanisms to improve farmers’ participation in priority setting process with regard to variety development and seed supply

This year the project promoted the establishment of links and exchange of experiences among seed producers of different areas with regard to seed supply. This in the sense of creating a critical mass of seed producers that may influence the near future the participation of farmers in priority setting process with regard to seed supply.

The exchange of experiences among potato farmers from Colomi (Prov. Chapare, Cochabamba) and Piusilla-Morochata (Prov. Ayopaya, Cochabamba) was made in October 2015.

The day of the event, held in the community of Piusilla, representatives of both groups developed oral presentations and practices. Piusilla experiences expressed in: organizational development, strengthening and marketing of native potato in regional and national markets (supermarkets, regional fairs); while Colomi producers of native potato shared their experiences in recovery seed diversity, production and marketing of seed potato.

- Sharing the experiences of the Association of Agricultural Producers San Isidro (APRA) – Piusilla/Morochata

Piusilla producers described their transformation as a group into three stages: 1) First, they were a group of producers organized in a Farmer Field School (FFS) and were trained in integrated potato crop management. 2) The group became a Local Agricultural Research Committee (CIAL, for its acronym in Spanish), conducted research on the agronomic management of potato cultivation and generated new potato varieties through PPB (Participatory Plant Breeding). 3) Finally, the group was organized in the Association of Agricultural Producers San Isidro (APRA). The transformation of the group lasted just over 20 years.

The Piusilla producers showed progress and experiences in developing and marketing bio-products, such as bio-fertilizers manure-based and mineral wines with sulfur and plant extracts. APRA commercializes these bio-products to local producers and to other regions.

APRA makes potato gourmet-type marketing in La Paz, Cochabamba and Santa Cruz. They sold weekly between 0.3 to 0.5 tons of potato gourmet-type. APRA members produce, select, pack and distribute potato to regular markets and supermarkets. APRA members do this work through a system of weekly shifts. The potato gourmet-type are small tubers (2-4 cm in diameter), which, in previous years, were intended for animal feed or simply left in the field because they were considered too small for human consumption.

Weekly delivery shifts are monitored by means of identifiers -pieces of wool of different colors- for each family (chimpu in Quechua), which allows traceability of the product in cases of returns. Sales are made to dealers who pay for the product through a bank account or direct payment in cash on delivery.

For the event, members of APRA conducted a practical demonstration of washing, sorting, packing and labeling of potato gourmet-type. The brand of this potato is "Morochatita" alluding to the prestige gained from Morochata region on good potato production.

The wash is conducted in a modified cement mixer, which has brushes rather than metal blades. The drying, sorting and bagging is done on a workbench with screens that help drain the water. The potato is packed in bags of one kilogram, it includes the brand, a cookbook and a piece of wool (chimpu) to identify the producer in charge of delivery.

Figure 3. Washing process by adapting a cement mixer, selection and packaging of potato gourmet-type produced by APRA in Piusilla – Morochata

- Sharing the experiences of native potato seed producers from Colomi

The Colomi seed producers exposed native potatoes, and reported the process of diversity restoration and recovery of seed vigor through use of high quality seed, use of healthy soils and temporal and spatial seed movements within the different ecological zones in the region of Colomi.

One of the main results of this exchange of experiences was the business plan with native potatoes gourmet-type, incorporating diversity to the current business. For this, native potato producers from Pico Central and Linde and producers of APRA, established links for the provision of native potato seed. Colomi producers delivered 80.5 kilos of good quality seed of six varieties of native potato to APRA. They will multiply and introduce those varieties in the future in the distribution channels at the level of regional markets, fairs and supermarkets nationwide, so that these actions led to the opening of the market for diversity of native potatoes.

Table 1. Quality seed of native potato delivered to APRA producers

| Variety | Quality | Quantity (kg) |
| --- | --- | --- |
| Mono Maki | Basic 3 | 12.5 |
| Sakampaya | Basic 3 | 15 |
| K´ellu Zapallu | Fiscalized | 3 |
| Puma Maki (Misi Chaki) | Basic 3 | 15 |
| Ñojcha Morada | Basic 3 | 32 |
| Ñojcha Negra | Fiscalized | 3 |
| TOTAL |  | 80.5 |

Output 2. Smallholder farmers are recognized not only recipient of technology and seeds, but are also providers of diversity and seeds

Activity 2.1 Providing training and capacity building on seed production, storage and commercialization among farmers in project sites

Provide equipment and infrastructures for seed production and storage at the community level

In 2015, two weighing scales (150 kg capacity) were acquired for the two groups of seed producers (Pico Central and Linde). Producers were trained in the use and maintenance of such equipment, and they defined internal rules of use and management of the weighing scales.

For the Pico Central group, the use of the weighing scale is restricted to be held in the seed storage silo, while producers of Linde Group can borrow the weighing scale for work in their fields. In both cases it has been designated a responsible for the administration of the weighing scale who must ensure that the equipment is in good condition at the time of the loan and return. If any damage occurred from misuse or damage by negligence, the responsible producers should bear the costs of repair or replacement.

Before producers have the weighing scales, the weight of the seed was made using manual scales and in many cases the weight of seed potato bags of 50 kg was estimated by eye by producers with more experience. This situation decreased the negotiating capacity of producers when marketing seed and common potatoes.

Figure 4. Delivery and use of weighing scales to the associations of seed producers Pico Central and Linde

Identify and document best farmers’ practices and traditional knowledge on seed production, storage, and commercialization

In 2015, traditional knowledge for production and refreshing seed potatoes were documented, as well as traditional storage systems for seed and common potato.

- Movements of the seed in time and in space

As explained earlier, the Puna of Colomi has three altitudinal levels: low puna (3250-3350 m), the intermediate puna or hillside (3350-3650 m) and high puna (3650 to 4200 m).

Seed flows in space and time using the different altitudinal levels of the Puna of Colomi is the traditional conservation strategy to maintain health and vigor of native potato seed.

Traditionally farmers conduct an exchange of seed, to revitalize the quality of the variety of interests and it is performed when the tuber seed loses health and productive force expressing low yields, tuber deformations and color changes of the foliage. In this state potato seed tubers are called locally "Sak'u" or "tired seed."

Potato farmers in the Andean region have learned that a change in environmental conditions can improve the health and revitalize the productive capacity of the seed potatoes.

Usually, in the first year, the seed is planted in the upper area or high puna (3750-4200 m) in the next agricultural season this seed is planted in the lower zone o low puna (3250-3350 m), and the third year, the seed is planted in the intermediate puna (3350 - 3750 m) and / or high puna, to restart the cycle.

Due to decreased access to land at different altitudinal levels of many families, and due to demand work and dedication to this practice, many farmers now choose to purchase seed at fairs in Colomi, Tiraque or Quillacollo, based on the principle that a change of altitude or growing region seed potatoes improve their productive characteristics. But, the seed that farmers gain from fairs has no guarantee of quality.

- Regeneration of seed potato tubers using botanical seed

This practice consists in recovery the most mature berries (fruits) of the potato variety whose seed is intended to renew. For this, farmers extract the botanical seeds from the berries and take out the mucilage that protects the seeds by washing with abundant water and ashes. The seed is dried in shade and stored in a dry place until planting time. Afterwards the seed is planted in a place where potato has not grown ever. The obtained seedlings are left to complete its cycle in the same place or are transplanted to a larger site, in both cases the resulting plants receive the same care as a normal potato crop. From this practice farmers get mini-tubers and they retain only the tubers that have the same characteristics as the parent variety (the rest of tubers are usually discarded). This material is cultivated by one or two crop years until the new tuber-seed scopes agricultural yields and expected behavior as the original variety.

This practice is rarely used today because demands hard work, time and patience to the farmer.

- Traditional storage systems

  - Storage housing

The storage - housing is a space condition in the family home, which is usually the bedroom where potato tubers are placed in piles, separated by trunks in a small space. This type of store is used for storing common potato and seed.

Houses that are used for storage are buildings with stone or mud walls uncoated, thatched occasionally with tile; the floor is usually covered with earth or concrete slab. Much of households have moderate diffuse light and ventilation through roof, cracks in the walls, windows and doors.

Figure 5. Selection and seed potato storage at silo housing

  - Phinas storage

The phinas are rustic silos conditioned in open space where air currents are frequent, in order to maintain stored tubers well ventilated and avoid rotting. This silo can store large volumes of potato tubers (0.5 to 3 tons of common or seed potato).

Phina conditioning involves a shallow soil excavation and fill this space with brave straw (Stipa ichu), then the farmer deposits sufficient amount of potatoes, completely covering the space excavated to form a pile of potatoes, tubers are finally covered with a thick layer of straw to protect them from sun, rain, wind, pests and animals.

Figure 6. Potato traditional silos Phina- type

  - Zarzo storage

Zarzos are rustic constructions type box inside the homes of native potato producers. These structures generally take the form of a rectangular tray 1 meter deep, two to three meters long. Although the dimensions depend on the amount of potato tubers that are to be stored.

Zarzos are built with local materials, generally trunks and branches of pine (Pinus sp.), eucalyptus (Eucalyptus sp.) and chilca (Braccharis sp.). Before storing the tubers, the walls of the zarzo must be completely coated with muña (Minthostachys sp.) and eucalyptus branches, which have the function of repellent plants for storage pests such as the potato moth (Symmetrischema tangolias). After depositing, the tubers are covered with a thick layer of eucalyptus leaves and muña.

Figure 7. Potato traditional silos Zarzo- type

Create and/or maintain information on nodal/custodian farmers

After consultation meetings, political administrative authority and representatives of communities of district Candelaria - Colomi, agreed to incorporate the category of crop diversity as a means to maintain and encourage the participation of custodian farmers at the Candelaria seed fair of native potato, which is held annually in April in this district. Henceforward, the fair aims to maintain in effect the presence of custodian farmers and diversity they hold.

The project facilitated the participation of custodian farmers of native potato from communities Pico Central and Linde in the seed fair of Candelaria - Colomi (12/April / 2015), where they brought a sample of the diversity of native potato they cultivate.

During the event, the organizers gave an award to the community it represented the custodian farmer who exposed more diversity.

Figure 8. Seed fair at Candelaria/Colomi (April 2015)

Provide training to existing and potential seed producers

The training topics prioritized in 2015 were: 1) Seed production (main crop pests and their control), 2) Commercialization, and 3) Management of soil fertility.

The training in seed potato production (pests, certification, storage and marketing) were developed with the support of an INIAF technician, and facilitated by the PROINPA technician and the local promoters as assistants. To reinforce the training sessions, booklets and factsheets developed by PROINPA Communication Unit were used.

Figure 9. Training of seed potato producers

The promotion and marketing knowledge were further strengthened through the exchange of experiences between Colomi producers and the Association of Agricultural Producers San Isidro (APRA), an organization from other region with extensive experience in seed potato production and marketing of potato gourmet-type (see activity 1.2).

Training sessions were initially focused on Pico Central and Linde/Pisly seed producer organizations (22 farmers). However, at the request of other families in the communities of Pico Central and Pisly, 95 additional potato producers were also trained in control of weevil and tuber moth. These trainings were developed during the monthly meetings of farmers’ organizations.

Table 2. Details of training sessions in 2015

| Training topics | Content sessions | Dates of training | Number of participants |
| --- | --- | --- | --- |
| Seed production | Main crop pests and control (phytopathogenic fungi, insects and nematodes) - Leoncio Morales (INIAF) Rhimer Gonzales (PROINPA) | 08/05/2015 (Pico central) 16/05/2015 (Linde) | Pico Central: 11 Linde – Pisly: 14 Additional farmers from Pisly: 55 Additional farmers from Pico Central: 40 |
|  | Seed storage (timely harvest, seed selection, storage) - Leoncio Morales (INIAF), Rhimer Gonzales (PROINPA) | 05/06/2015 (Pico central) 16/06/2015 (Linde) | Pico Central: 11 Linde – Pisly: 14 |
| Commercialization | Promotion and marketing of seeds, seed promotion in agricultural fairs, local promotion, marketing of seed quality, fair price and weight) - Leoncio Morales (INIAF), Juan Ruiz (APRA) | 03/07/2015 (Pico central) 16/07/2015 (Linde) | Pico Central: 11 Linde – Pisly: 14 |
| Management of soil fertility* | - How to improve soil fertility (crop rotation, cultivation of native legumes such as Lupinus mutabilis) - Disadvantages of using non-composted manure. - Composting manure with terrabiosa. Rhimer Gonzales (PROINPA) | July and August/2015 (monthly group meetings and field practices) | Pico Central: 11 Linde – Pisly: 14 |

* Training sessions on soil fertility includes participatory analysis of the main problems of using non-composted manure. Farmers concluded that the use of non-composted manure increased soil pests, plants are more susceptible to pests, harvested tubers rot faster and can store less.

The training was complemented with practical composting manure with seed producers of Pico Central and Linde / Pisly. They composted 90 cubic meters of manure (540 bags of 70 kg each) which was used to plant seven hectares of potato crops.

Figure 10. Composting manure in the communities of Pico Central and Linde/Pisly

Activity 2.2 Promoting the recognition of individual farmers and farmers associations who play an important role in providing good quality seed and supporting local seed systems

Publish and distribute list of local nurseries with details about crops, varieties and contact information of seed suppliers in project sites (continuous promotion of seed producers organizations through propaganda material and seed fairs)

The promotion of native potato seed producers was addressed through propaganda material and facilitating their participation in different seed fairs. In every event, seed producer organizations Pico Central and Linde distributed information (promotional leaflets) with details about varieties and contact information of seed suppliers.

In 2015, the project facilitated the participation of these two seed producer groups at the annual seed fair of Candelaria-Colomi (held in April every year) and the weekly fair of Colomi municipality.

At the fair in Candelaria, seed producers organizations Pico Central and Linde, promoted seed production of native potato and received recognition for their participation.

Figure 11. Promotion of native potato at the seed fair of Candelaria - Colomi

Seed of native potato were also promoted at the innovation fair of agriculture organized by COSUDE-Project of Continue Innovation (February 2015). The event was attended by over 50 farmers from 15 communities in the districts 2 and 3 of the Municipality of Colomi.

The project facilitated also the participation of seed producers at the Departmental Productive Meeting and Innovative Contest (organized by the Departmental Innovation Council of Cochabamba in June 2015) where farmers shared experiences on local seed systems of native potatoes in the highlands of the municipality of Colomi.

Also, the seed producers participated in the Tenth National Seed Fair and Business Roundtable (organized by the Ministry of Rural Development and Land and INIAF / July 2015). In this event Colomi seed producers exchanged knowledge about the production, promotion and marketing of seed.

Figure 12. Participation of native potato seed producers at the departmental contest of technological innovation and at the national seed fair

On the other hand, continued promotion of native potato seed in a retail store installed in the town center Colomi was performed. This promotion included the marketing of the seed planted by community groups from Pico Central and Linde/Pisly.

Figure 13. Continued promotion of native potato seed in the urban center of Colomi

Create and/or maintain registers of local varieties found in project sites and promote their recognition as commercial varieties

As a result of the approach of farmer seed producers of Pico Central to the INIAF, the registration process of seven native potato varieties began in 2014 for future seed certification. The process requires morphological characterization (using UPOV descriptors) in bloom and after harvest, which was done in February and June 2015. Along with the characterization information, the application for registration of varieties was presented to the INIAF Seed Office. See Annex 4 (Table of characterization) and (RC-01 form for the registration of new potato varieties in the National Seed System).

According to the rules of INIAF, registration of any variety has a cost that should be paid by the breeder. Although not specified in the rules, according to the INIAF the cost of registration of native varieties or landraces should be canceled by the enroller entity, in this case the producers of native potato seed. As this is a very high cost, INIAF decided to bear the costs of registration of two varieties of native potato (see Annex 5). The registration of the remaining native varieties that were characterized in 2015 was suspended, and it is pending until defining how to proceed in the future with this type of varieties.

Test out reward mechanisms to motivate the production of quality seed by farmers and increase demand for their seed

In consensus with seed producers, it was determined that two categories of native potato producers will be awarded:

• Growers of diversity (custodian farmers)

• Growers of high quality seed in trade volumes

Custodian farmers cultivate a high diversity of native potato varieties as part of their lifestyles, are collectors of varieties, and the main destination of this diversity is family consumption. Other farmers, neighbors and relatives turn to them to request seed of native varieties, so the custodians have high prestige in their communities.

The producers of high quality seed identified for recognition are those producers who are distinguished by following the principles of healthy seed production and offer seed in adequate volumes to sell in the local market.

Five farmers were identified and selected to receive an award according to these two categories. Incentives were granted in the form of agricultural inputs.

Table 3. Rewarded farmers as producers of quality seed and diversity of native potato

| Farmer’s name | Age | Community | Category |
| --- | --- | --- | --- |
| Teodoro Arroyo | 68 | Pico Central | Custodian farme |
| Juvenal Arroyo | 39 | Pico Central | Producer of high quality seed |
| Felix Zambrana | 60 | Pico Central | Producer of high quality seed and custodian |
| Renato Choque | 32 | Linde - Pisly | Producer of high quality seed |
| Aquilino Huanca | 65 | Pisly | Producer of high quality seed and custodian |

Promote local providers who supply quality diverse seed, for increasing farmers’ trust in such providers and creating demand of quality seed from them (demonstration plots)

Demonstration plots for potato production was established in 2014 (Alto San Isidro community), in order to promote the use of native potato seed originating from Pico Central and Linde. Seed from different origins was used: 1. Linde, 2. Pico Central, and 3. SEPA (the official seed supplier). Field days were scheduled during flowering and harvesting (in 2015) of these demonstration plots to evaluate the performance of the seed from Pico Central and Linde.

Yields (16 and 13 t/ha) using the local seed (Pico Central and Linde) were just slightly higher than the seed of SEPA (13 t/ha). These results demonstrate the good quality of local seed that is not less than the non-local certified seed. Participatory evaluations showed that potato farmers in the community of Alto San Isidro, are willing to pay a reasonable price for the seed that comes from the communities of Pico Central and Linde.

The second demonstration plot (800 m2) has been implemented in October 2014 with 4 quintals Category Basic 3 seed of varieties Imilla Negra and Canastillo originating from the Community of Pico Central.

This demonstration plot was harvested in May 2015 obtaining 33 quintals of selected seed (Table 4). The organization of seed producers Pico Central spent 22 qq of this seed (11 qq per variety) for replanting in the 2015-2016 crop year, and the remaining 11 quintals were sold as seed to other farmers in the agricultural fair Colomi. The resulting economic funds are administered by the organization.

Table 4. Seed production of native potato in demonstration plot of Pico Central

|  |  |  |  |  | Amount of selected seed (qq) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variety | Amount sown qq | Category sown 2014 | Seed origin | Category at harvest 2015 | II | III | IV | Total qq |
| Canastillo | 2 | B3 | Pico Central | R1 | 2 | 6 | 8 | 16 |
| Imilla Negra | 2 | B3 | Pico Central | R1 | 2 | 8 | 7 | 17 |

Participatory evaluations of farmers showed that the variety Canastillo (new variety in the area) has good prospects for marketing and preference for family consumption, due to its similar characteristics to the variety Yana Qoyllu (ancestral - local), which has great market demand and is good for local consumption. Therefore, farmers are expected to intensify Canastillo cultivation area. This variety is adapted to soil and dry climate making it an alternative to address the shortage of rainfall.

For the 2015-2016 crop year, other three demonstration plots with seed potatoes of Waycha and Candelero native varieties were planted in communities: Chimpa Rancho, Kanko and Pisly. The seed was provided by the seed growers groups Pico Central and Linde. In each plot 100 kg of seed was used. Producers are responsible for cultural practices and control of crop pests. At harvest they will return double the amount of seed used in the plot for the seed basket fund of the seed grower groups.

Field days and assessments on the performance of the crop at the time of flowering and harvest will be conducted in 2016.

Table 5. Demonstration plots planted in the 2015-2016 agricultural cycle

| Producer | Community | Altitude (masl) | Variety | Amount of seed (kg) |
| --- | --- | --- | --- | --- |
| Mateo Fernández | Chimpa Rancho | 3350 | Waycha | 100 |
| Aquilino Huanca | Pisly | 3800 | Candelero | 100 |
| Ricardo | Kanko - Huankuni | 3400 | Waycha | 100 |

Output 3. Crop varieties with variation in functional traits in respect of abiotic and biotic stress in crop varieties exists in the farmers’ production system

Activity 3.1 Making diverse portfolios identified in Activities 4.1. and 4.2. available through seed systems

Diverse portfolios: selection and process of multiplication

- Potato

Two portfolios of diverse varieties were identified for seed production in the first year of the project. Those are at different level of availability in the seed system.

The first portfolio of five varieties, all native cultivars, with high economic value and commercialization. Certified seed of those five varieties was bought from the formal seed system and then delivered to seed producers (two farmer associations) for multiplication purposes in the agricultural cycle 2013-2014, and 2014-2015. PROINPA provided technical assistance in the crop agricultural management. The competent authority (INIAF) certified the seed production of this material.

The second portfolio of seven varieties of native potatoes with potential economic value, were selected for production of pre-basic seed. Pre-basic seed is the highest quality seed produced from in vitro-plant virus-free. Pre-basic seed of four of those seven varieties (Candelero, Mono Maki, Puma Maki and Ñojcha Morada) plus another variety from the first portfolio (Pinta Boca) was produced obtaining seed at the end of 2014 in much more quantities than expected (Table 6) but in more time than planned, because of that the multiplication in the field was reprogrammed for the agricultural cycle 2015-2016. The pre-basic seed was stored in cold storage for seven months after harvest until planting time.

The other three varieties of the 2d portfolio and two additional varieties of the 3rd portfolio were still in process of virus cleaning in 2015 before pre-basic seed production (virus cleaning took more time than expected because we had to adjust protocols for virus cleaning). Virus cleaning of two varieties (Puca Qoyuqoyu and Ñojcha Negra) was not successful, then at the beginning of the agricultural cycle 2015-2016 we started the production of pre-basic seed of only three varieties with verified sanitary cleaning (Yuraj Qoyuqoyu from the 2d portfolio and Yana Qoyllu and Puca Qoyllu from the 3th portfolio).

While three portfolios of native potato varieties were determined (in total 14 varieties) since the beginning of the project, in the last months farmers have had greater preference for the production of four varieties (Pinta Boca from 1st portfolio, Candelero from 2nd and Yana Qoyllu and Puca Qoyllu from 3rd), due to they believe those varieties have more potential market in the short term.

Although in little quantities, Pinta Boca and Candelero are already available in the formal seed system, so some farmers could access to high quality seed investing their own resources. This is a direct impact on farmers, because they are now aware on the importance of injecting high quality seed in their seed systems.

Table 6. Pre-basic seed available for multiplication in the agricultural cycle 2015-2016

| Varieties | Seed (kg) | Portfolio | Observations |
| --- | --- | --- | --- |
| Mono Maki | 40 | 2 | Production with project |
| Puma Maki | 38 | 2 | Production with project |
| Ñojcha Morada | 13 | 2 | Production with project |
| Candelero | 46 | 2 | Production with project |
| Pinta Boca | 48 | 1 | Production with project |
| Puca Katawi* | 4 | 3 | Extra-seed obtained in the formal seed system |
| Imilla Negra | 4 | 1 | Extra-seed obtained in the formal seed system |
| Canastillo | 4 | 1 | Extra-seed obtained in the formal seed system |
| TOTAL | 197 |  |  |

* probably Puca Qoyllu

The multiplication in the agricultural cycle 2015-2016 of pre basic seed (Table 6) is being done individually (sown in 11 family plots) with the group of producers of native potato seed Linde / Pisly and communally in Pico Central (one plot).

In the community of Linde / Pisly pre-basic seed of Mono Maki (25 kg), Pinta Boca (28 kg), Puma Maki (23 kg) and Candelero (16 kg) is multiplied with producers in the form of company, which means that after harvest, total production will be distributed in two equal parts; one part goes to the producer, and the other part goes to the project administration.

The pre-basic seed of Mono Maki (15 kg), Pinta Boca (20 kg), Puma Maki (15 kg), Ñojcha Morada (13 kg), Puca Katawi (4 kg), Imilla Negra (4 Kg), Canastillo (4 Kg) and Candelero (30 kg) that is multiplied with the producers of Central Pico, after harvest the total production will be divided into three equal parts: one part will be distributed among the producers of the group, another part will go to the basket fund of the producer organization, and the last part will go to the project administration.

In the agricultural cycle 2014-2015, in the community of Pico Central, 11 varieties went through seed multiplication (categories B3 and B1 at sowing) in the field (aprox. 1 ha, communal plot).

At the end of this crop season, the following amounts of seed per variety (categories R2 and B2 at harvest) were reported in Pico Central: Category R1: Canastillo (2400 Kg.), Imilla blanca (3200 Kg.), Imilla negra (3100 kg). Category B2: Pinta Boca (30 kg.), Mono Maki (90 kg.), Ñojcha Morada (50 Kg), Ñojcha Negra (45 Kg), Puma Maki (90 kg.), Yana Qoyllu (360 Kg.), Candelero (360 Kg.) and Sakampaya (150 Kg.). This seed was distributed among 11 producers of native potato.

In the community of Linde-Pisly another communal plot of 1500 m were established in the agricultural cycle 2014-2015 with 5 varieties (Imilla Blanca, Imilla Negra, Pinta Boca, Candelero and Waycha). There were also other individual plots for seed multiplication with these and other varieties (e.g. Canastillo).

At the end of this crop season, the following amounts of seed per variety (categories R1 and B1 at harvest) were reported in Linde/Pisly (communal plot only): Category R1: Imilla Blanca (500 kg), Imilla Negra (500 kg) and Waycha (800 kg). Category B1: Pinta Boca (6 kg) and Candelero (6 kg). There are no records of seed production from the other individual plots. This seed was distributed among 11 producers of native potato.

The plots production in both communities were certified by INIAF (only registered varieties).

- Arracacha

In Tablas Monte, it has been established a plot mother of arracacha with 27 morphotypes. This material is the basis for the selection of diversity, where the project encourages producers to acquire seeds of the varieties that are interesting for them.

This genetic material has been evaluated in a participatory manner with farmers from Rio Negro community, identifying three early morphotypes (cycle of 270 days), 13 morphotypes with standard cycle for the species (305 days) and 6 late (365 days or more).

A replica of all germplasm was delivered to producers of Rio Negro, under the responsibility of Mr. Alejandro Rios.

All arracacha morphotypes available in Tablas Monte was conditioned for pre-rooting for purposes of multiplication and implementation of mother seed plots where the differences between the use of pre-rooted propagules and propagules planted directly will be evaluated in the agricultural cycle 2015-2016.

Figure 14. Preparation of arracacha propagules and conditioning of pre-rooting

In the agricultural cycle 2014-2015 two other family gardens of arracacha for seed production (400 m2 each) have been established with seven different morphotypes between white and purple root colors. Propagules from these gardens have been marketed (40 Bs / @ propagules) and gifted to producers of the neighboring community Maica Monte and to the same Tablas Monte community. The Yuraj (White), Kulli (Purple) and Cream (Mantequillero) morphs are in high demand by farmers for family consumption purposes.

In farmers’ land of Tablas Monte, the project promoted the establishment of 1.5 ha of arracacha (variety Kellu) where good culture practices was also implemented. Arracacha (edible roots) from these plots, was also sold at the Colomi fair between August and December 2015 at an average price of 125 Bs per 50 kg of roots arracacha. Root yields ranged from 24 to 29 tons / ha, depending on the time of harvest.

The producer’s organization of Rio Negro community bought 200 kg of seed-propagules from this plot to multiply arracacha in their community and have raw material for the production of bread for breakfast school.

Figure 15. Community Module of Rio Negro for making bread of arracacha, and producers of this root in the community.

Activity 3.2 Promote and monitor distribution of diverse portfolios of varieties identified in Activities 4.1 and 4.2. to farmers

Promote the adoption of diverse portfolios by organizing visits to demonstration plots for demonstration of functional traits

The multiplication plots of seed diversity established in September and October 2014 in Linde and Pico Central were also demonstration plots where good practices of culture were implemented. Demonstration tours and participatory evaluations in field days were scheduled for the flowering season and harvest in 2015.

Farmers from the communities of Alto San Isidro, Pisly and Kanko attended the field days. In February 2015 (flowering time) the field day was held in Pico Central community and in May / 2015 (harvest time) the field day was in Linde / Pisly.

At these events producers ratified the Pinta Boca, Yana Qoyllu and Candelero varieties like those of most interest for marketing purposes, while varieties Ñojcha Negra, Ñojcha Morada and Canastillo are preferred for home consumption.

These preferences are due to the commercial varieties of native potato, are an important source of income (although they are also popular for home consumption), are adapted to different environmental conditions of the region and are grown in large plots (1000 to 3000 m2) with yields reaching between 18-28 tons / ha. Native potato varieties intended for family consumption, normally lack market demand, therefore they are grown in small areas (300-500 m2) with yields between 12 to 16 tons / ha.

| A | B |
| --- | --- |

Figure 16. Demonstration plots of native potato seed (A) Central Pico, and (B) Linde / Pisly.

Make seed of diverse portfolios available in diversity fairs, through diversity kits and others

Whereas certified seed of various native varieties could be a means to promote their availability and access, the project contributed to the process of certification of diverse seeds.

In the agricultural season 2014-2015, the plots that met standards for certification of quality seed potato (use of certified seed, sown in free plots of pests, timely control of pests and weeds, harvesting, sorting, and storage) were certified by INIAF (National Institute of Agricultural and Forestry Innovation) technicians.

In Pico Central community, 14 plots with 57.5 qq native potato seed (mainly the first portfolio of varieties) of three categories of quality seed were established in the 2014-2015 agricultural cycle (Table 7).

Table 7. Amount of native potato seed established in the crop year 2014 - 2015 - Pico Central Community

| Varieties | Categories of certified seed |  |  | Total qq |
| --- | --- | --- | --- | --- |
|  | B1 | B3 | R2 |  |
| Canastillo |  | 4 |  | 4 |
| Candelero | 2 |  |  | 2 |
| Waycha |  | 10 | 28 | 38 |
| Imilla Negra |  | 6 |  | 6 |
| Yana Qoyllu | 1.5 |  |  | 1.5 |
| Imilla Blanca |  | 6 |  | 6 |
| Total | 3.5 | 26 | 28 | 57.5 |

After the certification process and selection of seed, 281 quintals of native potato seed quality (certified) were counted (Table 8). This seed represents aprox. 60% of total production registered by producers of the community. The remaining 40% of production was marketed as table potatoes, either because they did not meet the standards for seed or by decision of the producer due to the need for immediate income.

Table 8. Amount of native potato seed certified by INIAF at harvest in the 2014-2015 agricultural cycle - Pico Central Community

| Varieties | Categories of certified seed |  |  | Total qq |
| --- | --- | --- | --- | --- |
|  | B2 | R1 | C1 |  |
| Canastillo |  | 28 |  | 28 |
| Candelero | 7 |  |  | 7 |
| Huaycha |  |  | 176 | 176 |
| Imilla Negra |  | 31 |  | 31 |
| Yana Qoyllu | 7 |  |  | 7 |
| Imilla Blanca |  | 32 |  | 32 |
| Total | 20 | 91 | 176 | 281 |

In Linde/Pisly community, 21 plots with 35.6 qq native potato seed (mainly the first portfolio of varieties) of five categories of quality seed were established in the 2014-2015 agricultural cycle (Table 9).

Table 9. Amount of native potato seed established in the crop year 2014 - 2015 – Linde/Pisly community

| Varieties | Categories of certified seed |  |  |  |  |  | Total qq |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Pre-basic | B1 | B2 | B3 | R2 |  |  |
| Canastillo |  |  |  | 2 |  |  | 2 |
| Candelero | 0.1 |  |  |  |  |  | 0.1 |
| Waycha | 0.4 | 4 |  | 2 | 16 |  | 22.4 |
| Pinta Boca | 0.1 |  | 2 | 4 |  |  | 6.1 |
| Puca Waycha |  |  |  | 1 |  |  | 1 |
| Imilla Negra |  |  |  | 2 |  |  | 2 |
| Imilla Blanca |  |  |  | 2 |  |  | 2 |
| Total | 0.6 | 4 | 2 | 13 | 16 | 35.6 |  |

After certification process of the seed (2014-2015) by the INIAF, 209 quintals of high quality seed were accounted (Table 10).

Table 10. Amount of native potato seed certified by INIAF at harvest in the 2014-2015 agricultural cycle – Linde/Pisly community

| Varieties | Categories of certified seed |  |  |  |  | Total qq |
| --- | --- | --- | --- | --- | --- | --- |
|  | B1 | B2 | B3 | R1 | C1 |  |
| Canastillo |  |  |  | 8 |  | 8 |
| Candelero | 0.12 |  |  |  |  | 0.12 |
| Waycha | 4 | 22 |  | 13 | 99 | 138 |
| Pinta Boca | 0.12 |  | 15 | 24 |  | 39.12 |
| Puca Waycha |  |  |  | 6 |  | 6 |
| Imilla Negra |  |  |  | 9 |  | 9 |
| Imilla Blanca |  |  |  | 9 |  | 9 |
| Total | 4.24 | 22 | 15 | 69 | 99 | 209.24 |

Monitor level of distribution of diverse portfolios to farmers: keep records of where different materials went, in which amount, what crops and varieties, to whom

During field production continuous monitoring (weekly or fortnightly) of the plots by the technician and / or promoter were performed. After harvest, details of amount of produced seed, and its distribution were recorded.

Along with seed producers groups of Pico Central and Linde, the distribution record of seed production (certified and non-certified) from agricultural season 2014-2015, of the varieties of the first portfolio (Imilla Negra, Imilla Blanca, Canastillo, Pinta Boca and Waycha) was performed.

The following figure shows the amount of seed produced in the 2014-2015 crop season that has been destined at the re-planting (for multiplication purposes) in the agricultural cycle 2015-2016 by seed producers of Pico Central and Linde.

Figure 17. Amount of seed defined for re-planting in the agricultural cycle 2015-2016

The following figure shows the amount of seed produced in the 2014-2015 crop season that has been destined to sell by seed producers Pico Central and Linde.

Figure 18. Amount of seed destined to sell in 2015

The main site-destinations of seed potatoes produced by seed growers groups of Pico Central an Linde are listed in order of importance: the same community (mainly replanting), Colomi fair, Corani and Tablas Monte communities (tropic area), and communities of Candelaria district (Kuri Mayu, Palta Loma, Chimpa Rancho, Pisly and others) (Fig. 19).

Figure 19. Main site-destinations of native potato seed from Pico Central and Linde seed grower groups

Activity 3.3 Scale-up experiences

Inform, raise awareness, “convince” local and national authorities so that they support production and multiplication of foundation seed of diverse portfolios in the future

Colomi vocation as seed potato supplier of high quality is being driven by this project. Other producers from different communities that also have high lands want to join this initiative, as in the case of Palta Loma, neighboring community of Pico Central. The municipal and local (sindicatos) authorities have been informed about this initiative. However, the strengthening of seed producers groups and official recognition from the authorities is still ongoing, so that they support seed growers and multiplication diverse seed of high quality in the future.

Output 4. Tested technical schemes that use crop genetic diversity to reduce vulnerability (in terms of the probability of future crop or ecosystem services losses) developed

Activity 4.1 Create a catalogue of varieties with key functional traits and decide on packages or portfolios of varieties according to project sites’ key environmental constraints

At the suggestion of the managers of the institution, the catalog content of potato diversity with functional traits has been extended to other crops of agricultural biodiversity of Colomi in a context of climate change. Because of this expansion, still we do not have the printed version of the catalog, which is in the hands of the last technical reviewer (see catalog content in Annex 6).

Output 5. Recommendations and actions on how local, national and international institutions and strategies on plant genetic resources should address seed systems in their agendas

Activity 5.1. Evaluate existing policies and legislation in relation to how they affect the availability and exchange of genetic diversity

Organize workshops with different actors to share and discuss constraints derived from policies and laws, including plant variety registration and seed certification

Bolivia's current regulations regarding the protection of agricultural biodiversity, environment and mother earth, has gaps on issues related to traditional seed systems, particularly seed handled by small farmers. The lack of standards to ensure the quality of traditional native seed could generate the spread of pests and diseases that could affect the future health of soils, productivity and food sovereignty.

The project has been put this topic on the INIAF agenda of discussion, and in 2015, the project led to the organization of a workshop INIAF (National Seed Unit and Research and Genetic Resources Unit) to review current policies on seeds of agricultural biodiversity. The workshop should be held in late 2015, but was postponed to early 2016.

Conduct and document cost and benefit analysis of different models of: variety registration, seed quality certification and monitoring, centralized or decentralized seed production models, etc

This section shows case studies of production costs of native potato using seed of origin and quality known versus seed of origin and quality unknown. In addition, an analysis of the changes the project led in the livelihoods of beneficiary communities is presented at the end of this section.

The determination of production costs of native potato (var. Pinta Boca), included the compilation of primary data of two case studies from communities Linde and Pico Central, these data has been analyzed in a spreadsheet (Microsoft Excel), where costs per item, sales prices, total costs, net income, net profit and marginal return rate were calculated. Subsequently these data analysis were validated with members of the seed producer organizations Pico Central and Linde/Pisly.

The cost analysis was carried out based on 100 kg of seed potato of origin and quality known (Basic 3) compared with the same amount of seed of quality unknown acquired from Colomi local fair.

Fixed costs in potato production (either seed or table potato) are planting, cultural practices and phytosanitary control; while land preparation, seed, and harvest are variable costs. Table 11 shows that potato production for human consumption requires an estimated additional investment of Bs 230 ($ 33 US) which represents 7.5% of the total cost.

Table 11. Potato production costs (Bs.)

| Variables | Seed | Table potato |
| --- | --- | --- |
| Land preparation | 400.00 | 400.00 |
| Seed | 500.00 | 300.00 |
| Sowing | 811.00 | 811.00 |
| Cultural labors | 400.00 | 400.00 |
| Phytosanitary control | 234.00 | 234.00 |
| Harvest | 720.00 | 690.00 |
| Total Costs (Bs.*) | 3,065.00 | 2,835.00 |
| Total income (Bs.) | 4700.00 | 3550.00 |
| Net Income (Bs.) | 1,635.00 | 715.00 |

*1 Bs. = 0.144 $us

Table 12 shows that the productivity and yield with the use of quality seed is higher than with the use of seed of unknown origin. Consequently, total income or gross and net incomes are also higher with the use of quality seed that with the use of unknown quality-seed (Table 11 and 12). Although the sale price of seed potato at Colomi fair is the same as the potato consumption (regardless of the source or quality of the seed used), the yields obtained with good quality seed are higher than seed obtained with unknown quality (Table 12).

Table 12. Production and income from the sale of potatoes

| Tuber size | Unit | Income from the sale of native potatoes cultivated with known seed quality |  |  | Income from the sale of native potatoes cultivated with unknown seed quality |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Quantity | Unit Price (Bs.) | Total income (Bs.) | Quantity | Unit Price (Bs.) | Total income (Bs.) |
| Extra (large for human consumption) | bag * | 6 | 300 | 1800 | 4 | 300 | 1200 |
| Size 2 (for human consumption) | bag | 6 | 250 | 1500 | 5 | 250 | 1250 |
| Size 3 (for human consumption and seed) | bag | 4 | 200 | 800 | 4 | 200 | 800 |
| Size 4 (seed) | bag | 2 | 150 | 300 | 2 | 150 | 300 |
| Size 5 (seed) | bag | 2 | 150 | 300** | 2 | 0 | 0 |
| Gross income |  | 20 |  | 4700 | 17 |  | 3550 |

*1 bag = 100 kg

** All harvested tubers are used by the producer while they have quality and strength, which is expressed in a good performance and health of the tubers for many agricultural cycles.

The analysis of the changes the project led in the livelihoods (human, social, natural, physical and financial capitals) of beneficiary communities (group analysis in each community Pico Central and Linde) was conducted through the development of a matrix identifying and assessing the main local variables with respect to each capital (Table 13). This assessment was plotted on a pentagon of five capital livelihoods of farmers (Fig. 20).

Table 13. Participatory assessment of capital livelihoods

| PHYSICAL |  |  | SOCIAL |  |  | NATURAL |  |  | FINANCIAL |  |  | HUMAN |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Now | Before |  | Now | Before |  | Now | Before |  | Now | Before |  | Now | Before |
| Organizational infrastructure | 0.5 | 0 | Social economic organization | 0.5 | 0 | Access irrigation water | 0 | 0 | Farm income | 1 | 1 | Ancestral knowledge | 1 | 0.5 |
| Irrigation | 0 | 0 | Social activities | 0 | 0 | Forest resources | 0.5 | 0.5 | Other income | 0.5 | 0 | Traditional farming | 0.5 | 0.5 |
| Equipment and infrastructure for culture | 0.5 | 0 | Traditional activities | 0.5 | 0.5 | Own agricultural land | 1 | 1 | Pensions and allowances | 0 | 0 | New technology | 0.5 | 0 |
| Health center | 0 | 0 | Participation of community members | 1 | 0.5 | Improving soil quality | 0.5 | 0 | Economically active population | 0.5 | 0.5 | Gender Issues | 0.5 | 0.5 |
| Educational centers | 1 | 1 | Relations with other organizations | 0.5 | 0.5 | Landscape | 0.5 | 0.5 | Development of industries | 0 | 0 | Knowledge transfer (training) | 0.5 | 0 |
| Electricty | 1 | 1 |  |  |  | Climate | 0.5 | 0.5 |  |  |  |  |  |  |
| Drinking water | 1 | 1 |  |  |  | Diversity conservation | 1 | 0.5 |  |  |  |  |  |  |
| Improving production | 0.5 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Criteria: 8 | 4.5 | 3 | Total Criteria: 5 | 2.5 | 1.5 | Total Criteria: 7 | 4 | 3 | Total Criteria: 5 | 2 | 1.5 | Total Criteria: 5 | 3 | 1.5 |
| Punctuation | 2.81 | 1.88 | Punctuation | 2.5 | 1.50 | Punctuation | 2.86 | 2.14 | Punctuation | 2 | 1.5 | Punctuation | 3 | 1.5 |

| a | b |
| --- | --- |

Figure 20. Representation of changes in livelihoods (a) before and (b) after the project intervention

With regard to human capital, the native potato producers in Pico Central and Linde communities organized as groups of seed producers have improved their capital through the training and knowledge received in crop management and seed potato production under national rules to produce seed of high quality.

The social capital has been strengthened through the seed producers’ organizations and recognition as producers of quality seed locally (sindicatos and local government) and department level (INIAF). Before implementing the project, the communities of Pico Central and Linde/Pisly lacked productive organizations within their community structure; the new scenario has improved the capacity of communities to improve their productive economic structures due to they have a social arm of support for agricultural production and for the recovery and conservation of local diversity of native potato.

Natural capital was strengthened through the reinsertion of seed diversity of native potatoes, and the strengthening of production and access to high quality seed health (to date: 5 native varieties commercially focused, and 6 with future potential; and until the end of the project other 3 varieties), which is manifested in the recovery and increased crop diversity, accompanied by an improvement in yields and preservation of the health of the soil.

Physical capital of the zones of influence has been strengthened through the construction of seed storage silos, providing basic equipment to improve seed production such as improved plows to prepare plots, seed sorters and weighing scales.

Financial capital took place to a lesser extent in relation to the human, physical, social and natural capital, however, there is an improvement in the income of families as a result of the use of quality seed in the increase potato yields, as well as the sale of the seed. It is expected that this capital will be strengthened by the effects of increased production of quality seed and organizational strengthening for the business in the near future.

Activity 5.2 Propose options to enhancing the legal framework, so that they better serve seed providers’ and farmers’ needs, and, in particular, those that refer to variety egistration and seed certification schemes

As a result of some interactions with the national authority on seeds (INIAF) in 2014 and 2015, the project has outlined a proposal to implement the Quality Declared Seed System for potato. This document shows the magnitude of the importance of the traditional system in the supply and distribution of seed potatoes that provides more than 95% of the seed used in Bolivia. It also makes an analysis of the current public policy, which is favorable to the revaluation of knowledge, practices and knowledge of seed producer farmers who feed and sustain the traditional seed system. The document identifies barriers in the formal seed supply, but also identifies barriers in the traditional seed supply. Finally, the document shows a proposal for a revaluation of the traditional system of non-certified seed potato varieties, by implementing the Quality Declared Seed System, the latter developed by FAO (2006) (see draft document in Annex 7).

Additionally, the project has also developed a preliminary proposal of standards for seed production of native potato varieties under the Quality Declared Seed System format. This document shows the steps and requirements to fulfill that purpose. It Includes: (1) Facilities and equipment recommended (2) Collective (group, association, cooperative) or individual registration and Cross inspection, (3) Requirements of the land, (4) Field standards, (5) Cross inspections in the field, (6) Quality standards for seed tubers, and (7) Label (see draft document in Annex 8).

- Activities planned and not completed, and expected date of completion.

Each activity includes different sub-activities, which have different level of progress. Many are close to finish according to the expected final purposes of the project. A few have to continue the following last months of the project. In this report, the progress of planned sub-activities for the third year is on time according to the work plan, but some are delayed or have little progress. Those are explained below.

Activity 1.1 Understanding seed systems: actors involved, system’s capacity to provide crop diversity, system’s ability to adapt to changes, farmers’ preferences and choices

The data collection to assess the state of conservation of native potato diversity, which includes mapping varieties with functional features are still in process until early 2016 and we expect to have final results (systematization, analysis and conclusions) until April 2016.

Activity 1.2 Strengthening linkages between diversity of actors in the seed system

In meetings between the project, seed growers groups and seed unit of INIAF, the commitment to disseminate information and contact details of the seed producers Colomi in INIAF website was established, however to date not yet INIAF has published the information provided on the seed producers groups. We will continue to insist to fulfill this commitment.

Activity 2.1 Providing training and capacity building on seed production, storage and commercialization among farmers in project sites

In 2015, training sessions were conducted to strengthen the skills of Colomi seed producers in terms of marketing. These sessions were kindly addressed by an INIAF technician, and additionally seed producers learned about the experience on the subject, from another organization of potato producers from Morochata-Piusilla. Despite these efforts, Colomi seed producers said they still need more support in the areas of promotion and marketing seed potatoes. This is an indication that the issue of marketing is still weak and requires greater investment in terms of creating marketing plans and capacity of seed producers groups. It is expected to address this issue until the end of the project (July 2016).

Activity 2.2 Promoting the recognition of individual farmers and farmers associations who play an important role in providing good quality seed and supporting local seed systems

We believe that the registration process of native potato varieties has regressed. This is due to the lack of information and clarity in the internal rules of INIAF, who has no clear how to proceed with the registration of ancestral varieties. In 2014 farmers with support from the project, had begun the registration process for six varieties, but after the morphological characterization performed under INIAF standards, INIAF stopped and only continued the process with two of the six varieties. It is expected to put on the agenda for discussion this topic during the workshop on seed policy of agricultural biodiversity to be held in early 2016.

Activity 3.3 Scale-up experiences

The strengthening of seed producers groups and official recognition from the local authorities is still ongoing. The process of raise awareness and convince local and national authorities is a long and demanding process. The political agendas of the authorities has also adversely affected the process in 2015 because of the election of new authorities with whom we had to start all over again.

Activity 4.1 Create a catalogue of varieties with key functional traits and decide on packages or portfolios of varieties according to project sites’ key environmental constraints

At the suggestion of the managers of the institution, the catalog content of potato diversity with functional traits has been extended to other crops of agricultural biodiversity of Colomi in a context of climate change. Because of this expansion, still we do not have the printed version of the catalog, which is in the hands of the last technical reviewer. We expect to have the final and printed document during the first semester of 2016.

Activity 5.1 Evaluate existing policies and legislation in relation to how they affect the availability and exchange of genetic diversity

In 2015, the project led to the organization of a workshop INIAF (National Seed Unit and Research and Genetic Resources Unit) to review current policies on seeds of agricultural biodiversity. The workshop which should be held in late 2015, was postponed to early 2016.

- Assessment of progress, including opportunities and challenges

As explained in the activity 5.1, the project has contributed to positive changes in the livelihoods not only of the seed producers groups, but also indirectly in the livelihoods of the communities where the groups belong. The project has made significant advances in improving Colomi seed system; however, some actions have fallen short and are of concern to the project beneficiaries. It is the case on the need to inject seed highest quality (pre-basic) to the Colomi seed system periodically. In the framework of the project, injecting quality seed (pre-basic) was done every year, because as the seed is grown year after year, its quality decline, so a periodic refreshing of seed is needed. The seed producers are willing to invest in purchasing high quality seed in the future, but due to the high cost of the seed, the quantities purchased would be limited. Therefore, in the case of no more support projects, farmers ask support from local authorities and generate local policies to inject periodically high-quality seed to the production native potato system.

Another challenge is to develop a marketing strategy for seed diversity of native potato; this because some seed growers said that in some few years achieved good production, but they were limited in their ability to negotiate and did not have good sales. It is important to accompany not only production, but also the marketing of the seed to avoid bad business.

Another challenge is to achieve changes in current policies on seed. We realize that this process may be longer than the duration of a project; however, it is important to start discussions with the competent authorities of seeds. The discussion on this topic should be addressed at national level and at the level of local authorities, with whom shorter-term results could be obtained compared to negotiations with national authorities.

ANNEX 1.  Form of data collection using five-cell analysis and mapping potato plots

| 1 | EVALUACION DEL ESTADO DE LA DIVERSIDAD GENETICA DE PAPA EN COLOMI |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NOMBRE PRODUCTOR: JUAN FERNANDES |  |  |  |  |  |  | COMUNIDAD: Escalon (ladera) FECHA: 2 de DIC. 2015 |  |  |  |  |  |  |
| EDAD: 40 |  |  |  |  |  | RESIDENCIA(Coordenadas): S17°16'25,00"; W65°56'40,17" |  |  |  |  |  |  |  |
| MUCHAS FAMILIAS: Mayor a 6 |  |  |  |  |  | SUPERFICIE: | PARCELA GRANDE: 10-12 cargas de semilla |  |  |  |  |  |  |
| POCAS FAMILIAS: Menor a 6 |  |  |  |  |  |  | PARCELA PEQUEÑA: 1-2 Cargas de semilla |  |  |  |  |  |  |
|  |  |  | PRODUCE |  |  |  |  |  |  |  |  |  |  |
| CAMPO |  | N° | SI | NO | VARIEDADES | RASGOS FUNCIONALES (¿EL PORQUE?) |  |  |  |  | EPOCAS DE SIEMBRA |  |  |
| MUCHAS FAMILIAS PARCELAS GRANDES |  | 1 | X |  | Waycha | Buen mercado-rico en la cocina-suceptible a la enfermedad del tizon y kasparillo |  |  |  |  | Miska junio |  |  |
| POCAS FAMILIAS PARCELAS GRANDES |  | 1 | X |  | Yana qoyllu | Buena para comer, buen precio en el mercado, suceptible para el tojtu, kasparillo |  |  |  |  | Miska-junio, Jatun tarpuy-agosto |  |  |
| MUCHAS FAMILIAS PARCELAS PEQUEÑAS |  | 1 | X |  | Pinta Boca | Buen mercado y precio, resistente(fuerte) a enfermedades del tojtu y kasparillo |  |  |  |  | Miska-mayo y junio, jatun tarpuy-agosto, septiembre |  |  |
|  |  | 2 | X |  | Imilla Blanca | Bueno para comecio, muy suceptible al tojtu y kasparillo |  |  |  |  | Jatun tarpuy-agosto |  |  |
|  |  | 3 | X |  | Amajaya | Bueno para come, precio bajo en mercado, resistente al tojtu y kasparillo |  |  |  |  | Jatun tarpuy-septiembre |  |  |
|  |  | 4 | X |  | Pureja | Buen precio en el mercado, no conocen los comerciantes, suceptible al tizon |  |  |  |  | Miska-junio, Jatun Tarpuy- sep |  |  |
| POCAS FAMILIAS PARCELAS PEQUEÑAS |  | 1 | X |  | Holandesa | No produce bien en ladera si en zona baja |  |  |  |  | Miska-junio, Jatun tarpuy-septiembre |  |  |
|  |  | 2 | X |  | Candelero | Baja produccion por falta de semilla de calidad certificada, buen comercio y precio, suceptible al tojtu, kasparrillo |  |  |  |  | Jatun tarpuy-septiembre |  |  |
|  |  | 3 |  | X | Puca qoyllu | No hay buena semilla, comerciantes no conocen por el color, suceptible al tojtu. |  |  |  |  | Jatun tarpuy-agosto, septiembre |  |  |
|  |  | 4 | X |  | Rosita | Buena para papa frita, suceptible para la helada |  |  |  |  | Miska-junio |  |  |
|  |  | 5 | X |  | Doble H | precio bajo en el mercado, resistente a la enfermedad |  |  |  |  | Miska-junio,julio |  |  |
|  |  | 6 | X |  | Robusta | Buen comercio, suceptible al tijtu y kasparillo |  |  |  |  | Miska-junio,julio |  |  |
|  |  | 7 | X |  | Yana qoyllu | Buena para comer, buen precio en el mercado, suceptible para el tojtu, kasparillo |  |  |  |  | Miska-junio, Jatun tarpuy-agsto |  |  |
| PERDIDA DE VARIEDADES |  | 1 |  | X | Tanta Wawa | semilla cansada, bueno para comer, suceptible al tizon |  |  |  |  | miska |  |  |
|  |  | 2 |  | X | Chejchi kanastillo | No hay semilla, buen mercado, muy suceptible al Tizon |  |  |  |  | Jatun tarpuy-septiembre |  |  |
|  |  | 3 |  | X | kara wallaquito | bueno para comer, no hay semilla |  |  |  |  | Jatun tarpuy-septiembre |  |  |
|  |  | 4 |  | X | llusta | produce en la zona baja, buena para comer como chuño, suceptible al tizon y kasparillo |  |  |  |  | Jatun tarpuy-agosto |  |  |
|  |  | 5 |  | X | toralapa | produce en la zona baja |  |  |  |  | miska-junio, jatun tarpuy-sep |  |  |
|  |  | 6 |  | X | Chuisillu | No hay semill, buena para comer, buen precio para el mercado y venta |  |  |  |  | Jatun tarpuy-septiembre |  |  |
|  |  | 7 |  | X | Sani imilla | No hay semilla, precio muy bajo en el mercado, para comer malo y muy suceptible al Tizon y kasparillo |  |  |  |  | Miska-junio, Jatun tarpuy- septiembre |  |  |
|  |  | 8 |  | X | Runa criolla | buena para comer, No hay buen comercio, no produce bien, precio muy bajo, |  |  |  |  | Jatun tarpuy-septiembre |  |  |
|  |  | 9 |  | X | Lila | bueno para comer, semilla cansada, buen mercado, poco suceptible al tojtu kasparillo |  |  |  |  | Miska-julio |  |  |
|  |  | 10 |  | X | Kori Zongo | Comercio Bueno, bueno para comer, buen precio para el mercado, suceptible al tizon kasparillo |  |  |  |  | Miska-junio; Jatun Tarpuy-sep |  |  |
|  |  | 11 |  | X | Lunka Imilla | precio muy bajo en mercado, muy suceptible al tojtu |  |  |  |  | Miska-junio |  |  |
| TOTAL N° DE VARIEDADES |  | 24 | 12 | 12 | En la época de la Miska la siembra es para la venta. En la época de Jatun tarpuy la siembra es para el consumo y semilla, si sobra mucho llevan al mercado |  |  |  |  |  |  |  |  |

Mapping native potato plots belonging to Mr. Alvaro Montano - community Pico Central (slope)

ANNEX 2.

Example on INIAF invitation to seed producers of Pico Central to the departmental meeting of seed producers

Example of Act of compliance between the INIAF technical assistance and seed producers of Pico Central

INIAF invitation to seed producers of Pico Central to the National Seed Fair and Business Roundtable

ANNEX 3.

SCRIPT FOR PROMOTIONAL VIDEO

OUR NATIVE SEED POTATOES

(Spanish version)

1.- La organización.

Las organizaciones de productores de semilla de papa nativa están conformadas por hombres y mujeres organizados de las comunidades de Pico Central y Linde.

Nuestras comunidades están ubicadas en las zonas de altura del distrito de Candelaria, donde contamos con tierras sanas para la producción de semilla.

2.- Producimos semilla de papa nativa de calidad.

Estamos organizados y capacitados para la producción de semilla de calidad (Básica, Registrada y Certificada) de papa nativa de las variedades Huaycha, Yana Imilla, Yuraj Imilla, Yana Canastillo, Yana Qoyllu, Puca Qoyllu, Pinta Boca y otras

3.- Usamos semilla básica.

Para la multiplicación de esta semilla usamos semilla de Prebásica que compramos de SEPA a través de PROINPA.

4.- Sembramos en suelos sanos.

En las zonas de altura donde vivimos contamos con suelos Phurumas (sanos). Nuestras parcelas esta ubicadas entre los 3800 a 4100 metros de altura, en las cuales trabajamos de forma comunitaria.

5.- Producimos semilla sana.

Realizamos el control de enfermedades antes de la siembra, en la parcela, durante la cosecha y el almacenamiento, para que nuestra semilla esté libre de problemas como la Qaracha, Jullu y Chaki Unquy.

6.- Usamos productos naturales.

Para mejorar nuestra producción y cuidar el medio ambiente, elaboramos Biol como fertilizante y caldos minerales “Jampis” para controlar las plagas de la papa combinando con el control químico, así reducimos el daño al medio ambiente, al suelo y a nuestra salud.

7.- Nuestra semilla es certificada por el INIAF.

Todas nuestras parcelas son controladas tanto en campo como en almacén por la unidad de producción de semilla del INIAF quienes certifican que nuestra semilla cumple con normas nacionales de sanidad y calidad.

8.- Realizamos una selección y almacenamiento adecuado.

Nuestra semilla pasa por un control de la calidad por medio de la selección manual y es almacenada en silos especiales para papa semilla, que están ubicadas en las zonas altas de nuestras comunidades (más de 3800 metros de altura) donde no existen problemas de polilla.

9.- Promocionamos y comercializamos nuestras semillas.

La promoción de nuestra semilla es realizada en diversas feria organizadas por gobierno nacional y el INIAF y las ventas son realizadas en Pico Central; Linde, Pisly y Colomi.

ANNEX 4. Table of morphological characterization of varieties of native potato seed

| No. | UPOV Potato descriptors | Sakampaya | Puca Ñojcha | Yana Ñojcha | Yana Qoyllu | Candelero | Canastillo | Mono Maki |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Brote. Tamaño | 5 | 5 | 5 | 5 | 3 | 5 | 3 |
| 2 | brote: forma | 4 | 2 | 2 | 2 | 4 | 2 | 2 |
| 3 | brote: intensidad de la pigmentación antocianina en la base | 7 | 7 | 9 | 7 | 7 | 7 | 9 |
| 4 | brote: proporción de azul en la pigmentación antocianina en la base | 3 | 3 | 3 | 3 | 3 | 3 | 3 |
| 5 | brote: pubescencia en la base | 9 | 7 | 7 | 7 | 3 | 7 | 3 |
| 6 | brote: tamaño del extremo en relación con la base | 5 | 3 | 3 | 5 | 5 | 5 | 3 |
| 7 | brote: porte del extremo | 3 | 3 | 3 | 3 | 3 | 3 | 3 |
| 8 | brote: pigmentación antocianina del extremo | 1 | 7 | 9 | 7 | 7 | 7 | 5 |
| 9 | brote: pubescencia del extremo | 1 | 1 | 1 | 7 | 7 | 7 | 1 |
| 10 | brote: número de radículas | 7 | 5 | 5 | 5 | 5 | 5 | 7 |
| 11 | brote: longitud de las ramificaciones laterales | 5 | 3 | 3 | 5 | 3 | 5 | 5 |
| 12 | Planta: estructura del follaje | 2 | 2 | 2 | 2 | 2 | 2 |  |
| 13 | Planta: porte | 5 | 5 | 5 | 5 | 3 | 3 |  |
| 14 | Tallo: pigmentación antocianina | 1 | 5 | 7 | 5 | 7 | 9 |  |
| 15 | Hoja: tamaño del contorno | 3 | 3 | 3 | 7 | 7 | 7 |  |
| 16 | Hoja: apertura | 5 | 5 | 5 | 5 | 5 | 5 |  |
| 17 | Hoja: presencia de folíolos secundarios | 3 | 3 | 3 | 5 | 5 | 3 |  |
| 18 | Hoja: color verde | 3 | 5 | 5 | 5 | 7 | 7 |  |
| 19 | Hoja: pigmentación antocianina del nervio central del haz | 1 | 5 | 5 | 5 | 7 | 9 |  |
| 20 | Segundo par de folíolos laterales: tamaño | 3 | 5 | 5 | 5 | 3 | 5 |  |
| 21 | Segundo par de folíolos laterales: anchura en relación con la longitud | 5 | 5 | 5 | 5 | 3 | 5 |  |
| 22 | Folíolos terminales y laterales: frecuencia de la coalescencia | 5 | 5 | 5 | 5 | 5 | 5 |  |
| 23 | Folíolo: ondulación del borde | 5 | 5 | 5 | 5 | 5 | 5 |  |
| 24 | Folíolo: profundidad de los nervios | 5 | 5 | 5 | 5 | 5 | 5 |  |
| 25 | Folíolo: brillo del haz | 5 | 5 | 5 | 5 | 7 | 5 |  |
| 26 | Folíolo: pubescencia del haz en la roseta apical | 1 | 1 | 1 | 1 | 1 | 1 |  |
| 27 | Botón floral: pigmentación antocianina |  | 7 | 3 | 9 | 5 | 9 |  |
| 28 | Planta: altura | 3 | 5 | 5 | 5 | 7 | 7 |  |
| 29 | Planta: frecuencia de flores |  | 5 | 5 | 7 | 5 | 9 |  |
| 30 | Inflorescencia: tamaño |  | 5 | 5 | 5 | 5 | 5 |  |
| 31 | Inflorescencia: pigmentación antocianina del pedúnculo |  | 7 | 7 | 7 | 7 | 9 |  |
| 32 | Corola de la flor: tamaño | 5 | 7 | 7 | 7 | 5 | 7 |  |
| 33 | Corola de la flor: intensidad de la Pigmentación antocianina de la cara interna | 9 | 9 | 9 | 9 | 7 | 9 |  |
| 34 | Corola de la flor: proporción de azul en la pigmentación antocianina de la cara interna | 2 | 3 | 3 | 3 | 3 | 3 |  |
| 35 | Corola de la flor: extensión de la Pigmentación antocianina de la cara interna | 7 | 7 | 7 | 9 | 7 | 9 |  |
| 36 | Planta: época de madurez | 7 | 9 | 9 | 9 | 9 | 5 | 9 |
| 37 | forma del tubérculo | 5 | 3 | 3 | 3 | 3 | 5 | 5 |
| 38 | tubérculo: profundidad de los ojos | 3 | 9 | 9 | 9 | 9 | 7 | 3 |
| 39 | tubérculo: color de la piel | 1 | 3 | 3 | 3 | 3 | 3 | 5 |
| 40 | Tubérculo. Color de la base del ojo | 3 | 3 | 3 | 3 | 3 | 3 | 4 |
| 41 | tubérculo: color de la pulpa | 4 | 4 | 4 | 4 | 4 | 2 | 2 |

RC-01 form for the registration of new potato varieties in the National Seed System

ANNEX 5. Act INIAF commitment to register two varieties of native potatoes (Canastillo and Ñojcha Morada)

ANNEX 6. Catalog Content

TITLE: La agrobiodiversidad de Colomi en un contexto de cambio climático

PRESENTACION

I.	AGROBIODIVERSIDAD Y CAMBIO CLIMATICO

1.	Marco conceptual

- Variabilidad climática, cambio climático y vulnerabilidad

- Efectos del cambio climático

- Agroecosistemas y agrobiodiversidad

2.	Características del Municipio de Colomi

3.	Manejo de la Agrobiodiversidad en el Municipio de Colomi

- Aspectos ecológicos

- Distribución espacial de la agrobiodiversidad

- Factores relacionados con el manejo de la agrobiodiversidad

- Disponibilidad de bienes y recursos

- Relacionamiento con el entorno

- Aporte nutricional y económico de la agrobiodiversidad en Colomi

4.	Percepción local del cambio climático

5.	Estrategias locales de adaptación al cambio climático

6.	Consideraciones finales

II.	DIVERSIDAD AGRICOLA DE LA ZONA DE PUNA DEL MUNICIPIO DE COLOMI

TUBERCULOS ANDINOS

- Papa

- Oca

- Papalisa

- Isaño

LEGUMINOSAS

FRUTALES

BIBLIOGRAFIA

ANNEX 7.

Draft Proposal for the implementation of the Quality Declared Seed System in Bolivia

(Spanish version)

Antecedentes

El mejoramiento de la calidad de las semillas es un factor fundamental para incrementar el potencial de rendimiento de los cultivos y es uno de los medios más económicos y eficientes para mejorar la producción y productividad agrícola

En muchos países los programas nacionales de semillas desarrollaron la producción formal de semillas en respuesta a la necesidad de contar con sistemas de abastecimiento de semillas más seguros que permitieran poner a disposición de los agricultores semillas de buena calidad de variedades mejoradas. No obstante, las expectativas en cuanto al desarrollo de la industria de semillas resultaron ser demasiado optimistas y no se cumplieron por razones complejas.  Como consecuencia, la proporción de semilla formal que realmente llega al mercado y a los usuarios por los canales formales es extremadamente baja.

En el caso de la papa en Bolivia, la producción para el periodo 2005-2007se realizó en una superficie media de 126.943 ha (Zeballos, economía de la papa, 2009).  Esta referencia permite estimar que el requerimiento aproximado de semilla a nivel nacional es de aproximadamente 190.000 tn de semilla por año considerando que se emplea en promedio 1,5 tn de semilla por hectárea.

El sistema formal de semilla el año 2013, abarcó una superficie de 1340,86 ha que permite una oferta de 9721,98 t de semilla certificada de 22 variedades, de las cuales, dos variedades representaron el 95 % de la producción: 68 % Desiree (introducida) y 27 % Huaycha (nativa) (Informe anual 2013 de la Dirección Nacional de Semillas del INIAF). En base a la información precedente se estima que la oferta actual de semilla certificada constituye apenas el 5 % del requerimiento anual de semilla de papa en Bolivia. El predominio de dos variedades en la oferta de semilla certificada de papa en sus diferentes categorías indica que el sistema formal se focaliza principalmente en la atención de la demanda de semilla de papa de variedades más cosmopolitas (que se adaptan inclusive a los valles mesotérmicos y trópico de Bolivia) y de alto valor comercial.

El balance entre la oferta de semilla certificada y la demanda potencial de semilla de papa en Bolivia permite visualizar la magnitud de la importancia del sistema tradicional en el abastecimiento y distribución de semilla, denominada como informal, que aporta el 95 % de la semilla utilizada en el territorio nacional y en gran medida constituye autoabastecimiento. El portafolio de variedades que fluye en el sistema tradicional es amplio y varía en función a las preferencias regionales (Zeballos, et al, 2009). Esta constatación, refuerza el rol preponderante del sistema tradicional de semilla en el fortalecimiento de las dinámicas comunales en el manejo de la agrobiodiversidad ligada a la seguridad alimentaria de miles de familias y comunidades vulnerables de la región del Altiplano, Puna y Cabeceras de Valle y Valles del territorio boliviano. La gran mayoría de los productores de papa especialmente de pequeña escala o familiares en las zonas altas se abastecen de semilla proveniente del sistema tradicional ya sea como semilla propia o semilla adquirida y distribuida localmente mediante circuitos o flujos de semilla no certificada que con luces y sombras están vigentes hasta la actualidad.

Política pública actual favorable a la revalorización de los conocimientos, prácticas y los saberes de agricultores semilleristas que alimentan y sostienen el sistema tradicional de semillas.

Bolivia se encuentra en un proceso de transformación en cuanto a la política pública después de su refundación. La nueva CPE plantea conceptos socialmente innovadores y nuevos paradigmas de desarrollo integral  como el “vivir bien” que busca la armonía entre los seres humanos y la naturaleza, promoviendo al mismo tiempo la satisfacción de las condiciones materiales y espirituales de las poblaciones (Orellana, 2013). La conservación de la biodiversidad, los recursos genéticos y la revalorización de los saberes locales son componentes sustancialmente incorporados en las estrategias y política pública como la Ley 144 de revolución productiva comunitaria, y la ley 300, marco de la Madre Tierra (Pacheco 2013). El contexto emergente de política pública que se encuentra en proceso de implementación, representa una oportunidad para revalorizar la semilla de variedades nativas de papa (lamentablemente considerada hasta ahora como informal), los conocimientos y saberes locales que junto a sus valores culturales y sociales hacen al sistema tradicional de producción que alimenta a la gran mayoría de los bolivianos.

Las bases y orientaciones de la política del vivir bien se establecen especialmente en la Ley 300 Marco de la Madre Tierra y desarrollo integral para vivir Bien, una norma que plantea varios artículos relacionados a promover una agricultura sostenible dentro de la conservación de la agrobiodiversidad y de alimentos nutritivos para la seguridad alimentaria con soberanía, garantizando el acceso a factores y medios de producción de alimentos, tierra, agua, semillas, mercados justos, tecnología y asistencia técnica, entre otros, en particular, para pequeños productores campesinos e indígenas. Entre los enunciados más relevantes asociados a la revalorización del sistema tradicional de semillas podemos citar los siguientes:

- Reconocimiento y fomento a la diversificación de la producción, la diversidad de los productos en los mercados, las practicas de intercambio comunitarios y en la dieta alimentaria, la protección a las variedades locales y nativas, asi como el fomento a las culturas y tradiciones alimentarias (Titulo II, Capítulo IV, articulo 13, párrafo 4)

- Acciones para evitar la mercantilización de los recursos genéticos, la privatización del agua, la biopiratería y el traslado ilegal de material genético, asi como la participación de monopolios y/o oligopolios en la producción y comercialización de semillas y alimentos. (Título II, Capítulo IV, articulo 13, párrafo 5)

- Revalorización y fortalecimiento de los sistemas de vida de los pequeños productores, de las naciones y pueblos indígena originarios campesinos, comunidades interculturales y afrobolivianas, cooperativas y otros sistemas asociativos, a través del manejo sustentable de su bioidversidad y del respeto, revalorización y reafirmación de sus saberes en el marco de la diversidad cultural. (Título II, Capítulo IV, articulo 13, párrafo 10)

- Fortalecimiento de las prácticas productivas locales para el uso y aprovechamiento de los componentes de la madre tierra, fortaleciendo los medios de vida, capacidades organizacionesles y habilidades de poblaciones locales en el marco del manejo múltiple y diversificado de las zonas de vida. (Título II, Capítulo IV, articulo 16, párrafo 7)

- Priorizar e incentivar la agricultura, pesca, ganadería familiar comunitaria y la agroecología, de acuerdo a la cosmovisión de cada pueblo, con un carácter diversificado, rotativo y ecológico para la soberanía con seguridad alimentaria buscando el diálogo de saberes. (Título III, Capitulo I, articulo 24, párrafo 5).

Así mismo, la Ley 144,  de la revolución productiva comunitaria agropecuaria entre sus alcances plantea el manejo sostenible y adecuado del agua y los recursos genéticos para garantizar los procesos productivos, promoviendo el proceso de gestión territorial indígena originaria campesino, comunidades interculturales y afrobolivianas y fortaleciendo las capacidades orgánicas, productivas, de transformación, comercialización y financiamiento, desde un enfoque intercultural que recupere los saberes, prácticas y conocimientos ancestrales.

Más específicamente en el artículo 13, (POLÍTICA DE FORTALECIMIENTO DE LA BASE PRODUCTIVA) la Ley 144 plantea fortalecer de manera integral la base productiva con énfasis en las prácticas locales y ancestrales de las comunidades para una gestión integral que optimice el uso y acceso al agua para riego, la recuperación de la fertilidad del suelo y la conservación e incremento de la biodiversidad a través de la recuperación y crianza de semillas nativas y producción de semillas mejoradas. Se promoverá y protegerá la producción, uso, conservación e intercambio de semillas de alta calidad que garanticen su provisión para la producción, mediante el estímulo a la recuperación, conservación, mejoramiento, producción y difusión de semillas nativas provenientes de los pueblos indígena originario campesinos, comunidades interculturales, afrobolivianas y de pequeños productores.

Es evidente que la normativa actual de certificación formal de semillas no toma en cuenta muchos de los conceptos y preceptos mandatorios mencionados tanto en la Ley Marco de la Madre Tierra como en la Ley 144, que establecen un marco legal muy favorable a la producción tradicional de semillas. En ese sentido, la coyuntura de política pública relativa a la revalorización de las semillas constituye una oportunidad para la revalorización de las semillas nativas que fluyen en el sistema tradicional generando mecanismos alternativos pero complementarios al sistema formal, que sean más sencillos en su aplicación para acreditar el proceso de producción tradicional de semilla de variedades nativas de papa. Esto es posible si se institucionalizan normas y procesos de producción de semilla que estén basados en la amplia experiencia,  los conocimientos y saberes ancestrales de las comunidades productoras de papa y de esta manera asegurar estabilidad en la calidad de semilla ofertada por una red de productores de semilla formalmente reconocidos que se refleje en mejores rendimientos para los usuarios.

Identificación de barreras en el abastecimiento de semilla formal:

La normativa de certificación de semilla de papa en Bolivia, establece que: “Solamente se podrán producir, comercializar, distribuir o donar semilla de variedades que hayan sido inscritas en el Registro Nacional de Variedades (RNV) que son las que pueden ingresar en el proceso de certificación y fiscalización de semillas.” (Registro Nacional de Variedades y de Variedades protegidas) y no se establecen excepciones ni complementaciones relacionadas a la amplia cantidad de variedades nativas de papa existentes en el territorio nacional. Esta disposición toma en consideración principalmente a las variedades provenientes del mejoramiento genético y por lo tanto de alguna manera margina a una gran cantidad de variedades nativas que no están inscritas en el RNV.

El registro de una variedad presenta complicaciones técnicas y prácticas que inviabilizan la posibilidad de registrar todas o al menos la mayoría de las variedades bolivianas de papa porque se debe cumplir con:

a) aprobar la prueba de identidad varietal que determina la condición distinta (en al menos una característica de otras variedades inscritas en el RNV), homogénea y estable  y

b) aprobar la prueba de valor agronómico que implica realizar pruebas de campo.

Estos requisitos están orientados principalmente a variedades obtenidas mediante procesos de mejora genética pero son poco aplicables para la enorme cantidad de variedades tradicionales o nativas que son cultivadas en las comunidades, por lo siguiente.

El registro de variedades es un requisito previo para iniciar el proceso de certificación. Bolivia como parte del centro de origen de éste cultivo, tiene más de mil variedades nativas de las cuales menos del 2 % están actualmente registrados. Ampliar sustancialmente el registro de variedades es operativamente complicado de lograr en un corto o mediano plazo por la implicación de costos que representa realizar las pruebas de campo y la descripción morfológica de la variedad.

El proceso técnico de la certificación limita la cobertura de la inscripción y sobre todo la inspección de los campos de cultivo cuando se trata de atender a una cantidad masiva de productores. Las dificultades técnicas son apreciables si se examina el proceso de certificación que se resume en los pasos siguientes:

- Pre-inscripción de los semilleristas identificando la superficie y número de cooperadores.

- Inscripción de los campos de cultivo: contrato de prestación de servicios entre la Oficina Regional de Semillas (ORS) y los productores.

- Inspección de campos de semilla: 60 a 100 días después de la siembra donde se evalúa la calidad fitosanitaria del campo semillero y se establecen los porcentajes permitidos de tolerancia descritos en el siguiente cuadro:

*Plantas anormales.- Se consideran como tales a todas aquellas plantas que estén afectadas por: Virus, Erwinia, Mutaciones y Micoplasmas.

- Aprobación o rechazo de la superficie inscrita: esta se realiza en función a una evaluación de plagas y enfermedades no permisibles: Machitez bacteriana (Ralstonia solanacearum), Verruga (Sinchytrium endobioticum), Carbón (Thecaphora solani)  y el nematodo del nódulo (Meloidogyne incognita)

- 8rma Específica para la Certificación de Semilla de Papa -R.M. 101 del 1 de octubre de 999

Realizada la inspección de campo, la semillera o semilleristas deberán ser informados inmediatamente sobre las decisiones de descenso de categoría o rechazo de campos semilleros, pudiendo en primera instancia solicitar una re-inspección.

- Inspección de tubérculos en almacén y muestreo: Volumen de semilla estimado de la categoría correspondiente

- Almacenamiento y comercialización: selección,  clasificación, etiquetado y almacenamiento

Sin duda el proceso es de alta exigencia en el cumplimiento de los requisitos. A ello se suma el uso de semilla inicial de categorías altas como la Básica que tiene costos elevados difíciles de asumir por los agricultores a pequeña escala lo cual desincentiva la adscripción de los mismos al sistema formal de certificación.

La oferta de semilla certificada, si bien cuenta con garantías de sanidad, es de lejos insuficiente en volumen y diversidad (reducido portafolio de variedades) para abastecer la demanda de semilla de papa a nivel nacional (G. Thiele, ). Consecuentemente, el acceso a semilla de calidad se ve considerablemente limitada para los productores de papa a pequeña escala o familiar que constituyen la gran mayoría de los productores de papa en Bolivia, incrementando la vulnerabilidad especialmente de los agricultores más pobres.

Identificación de barreras en el abastecimiento de semilla tradicional:

El sistema tradicional de semilla tiene alta capacidad de difundir semilla económicamente accesible y de un portafolio amplio de variedades que en Bolivia varía por regiones. Los agricultores tienen tecnologías que les ayudan a mantener la calidad de la semilla, pero no todos siguen las mejores prácticas y existen deficiencias generales que han generado una duda y desconfianza preocupante sobre la calidad de la semilla proveniente del sistema tradicional sin importar la procedencia o variedad (Thiele, 1999). No obstante, el sistema tradicional ofrece semilla de variedades que los agricultores quieren, a través de canales que ellos conocen (De Hann S,  p.139).

La pérdida de credibilidad respecto a la calidad de la semilla que fluye en el sistema tradicional constituye uno de los factores remarcables que está debilitando las funciones sociales, ecológicas y económicas  de un sistema que tradicionalmente ha estado basado en la confianza mutua en contraste a la certificación. El movimiento indiscriminado de semilla suscitado por la dinámica de las ferias rurales, implica también el movimiento de enfermedades y plagas (con especial atención en enfermedades como nematodos, rizoctonia y verruga) que riesgosamente se están diseminando por todo el país vulnerando la sostenibilidad de todo el sistema de producción de papa.

Las ferias rurales regionales o locales actualmente constituyen el principal nodo de distribución de semilla. Desafortunadamente, en las ferias se evidencia ausencia de mecanismos de control de la calidad de la semilla y un proceso de especulación con relación a la comercialización de semilla no certificada que tiende a agudizar la incertidumbre sobre la calidad de la semilla tradicional. Esta situación se explica porque la valoración local de la calidad de la semilla tradicional toma en cuenta criterios físicos y visuales como el tamaño (generalmente mediano o pequeño) apariencia sana (por ejemplo sin pudriciones) y presencia de brotes vigorosos pero también considera criterios subjetivos ligados a la percepción colectiva del prestigio que ciertas zonas y proveedores han adquirido por su especialidad en la producción de la semilla.

Propuesta de revalorización del sistema tradicional de Semilla no certificada de variedades nativas de papa en Bolivia, mediante la implementación del Sistema de Semillas de Calidad Declarada, desarrollada por la FAO (2006).

Concepto y principios del Sistema de Semillas de Calidad Declarada:

EL Sistema de Semillas de Calidad Declarada es una alternativa que puede utilizarse en cultivos, áreas y sistemas agrícolas en los cuales otros sistemas altamente desarrollados de control de calidad como el formal son difíciles de aplicar o tienen un impacto relativamente bajo.

El Sistema de Semillas de Calidad Declarada no pretende competir con otros sistemas existentes de control de calidad de semillas ni duplicar el trabajo de otras organizaciones especializadas, por el contrario puede ser complementario para cubrir fácilmente variedades de cultivos que por diferentes razones no se adaptan a los sistemas convencionales o formales de control de calidad de semillas.

El Sistema de Semillas de Calidad Declarada es un sistema práctico y relativamente simple en su ejecución contribuyendo a la diversificación del abastecimiento de semillas de modo que los agricultores puedan tener más oportunidades productivas accediendo a semilla de calidad y de bajo costo. Uno de los desafíos principales al diseñar un Sistema de Semillas de Calidad Declarada es que sea flexible en su ejecución pero que al mismo tiempo respete los principios básicos de calidad de semillas, de modo de contar con la confianza de todos los interesados y cumplir una función importante en el desarrollo del sector de semillas. El sistema se basa en el hecho de que la etiqueta adherida al envase de semillas representa la calidad de su contenido y todo el proceso de actividades que han contribuido a esa calidad. Si se pierde la reputación de la etiqueta debido a una mala supervisión, la esencia del sistema deja de ser válida. O, peor aún, esa etiqueta puede tener un impacto negativo.

USOS DEL SISTEMA DE SEMILLAS DE CALIDAD DECLARADA

El Sistema de Semillas de Calidad Declarada puede ofrecer un punto de entrada de bajo costo a cooperativas, grupos de agricultores, fincas privadas grandes y organizaciones no gubernamentales hacia actividades relacionadas con calidad de semillas sobre todo para el mercado interno dentro de un país.

El Sistema se basa en cuatro puntos fundamentales:

1. Una lista de variedades aptas para producir semillas como Semillas de Calidad Declarada.

2. Un registro de productores de semillas en la autoridad nacional pertinente.

3. Inspección en campo por parte de la autoridad nacional de al menos el 10 por ciento de los cultivos para semillas.

4. Inspección por parte de la autoridad nacional de al menos el 10 por ciento de las semillas que salen a la venta bajo la designación de Semillas de Calidad Declarada.

El sistema de semillas de calidad declarada implica desarrollar un conjunto de normas mínimas y los procedimientos a seguir para que un lote de semillas pueda ser designado como Semillas de Calidad Declarada. Para ello, la semilla debe ser originaria de un cultivo para el cual se establecen las normas y procedimientos adecuados. Actualmente se han desarrollado estas normas y procedimientos para muchas especies pero lamentablemente no incluyen la papa nativa. Una vez desarrollado y satisfecho las normas y procedimientos establecidos, el gobierno a través de la instancia competente puede autorizar la designación de SEMILLA DE CALIDAD DECLARADA.

Especies para las cuales se han desarrollado normas y procedimientos para la designación de Semilla de Calidad Declarada

Cereales y seudocereales:

Kiwicha,  Avena, Cebada, Arroz (polinización abierta), Arroz (híbrido), Mijo perla (polinización abierta y variedad sintética), Mijo perla (híbrido), Centeno, Sorgo (polinización abierta), Sorgo (híbrido), Trigo, Maíz (polinización abierta), Maíz (híbrido).

Leguminosas alimenticias:

Guandul, Garbanzo, Lenteja, Frijol, habichuela, poroto, Arveja, Haba, Frijol mungo, Caupí.

Cultivos oleaginosos:

Maní, Colza, Mostaza, Soja, Girasol (polinización abierta), Girasol (híbrido), Sésamo.

Especies forrajeras – Poaceae:

Camus, Cebadilla, Pasto Rhodes, Pasto ovillo, pasto azul, Festuca alta, Raigrás italiano, Panicum maximum Jacq, Pasto colorado, Pasto miel, Pasto kikuyo, Setaria incrassata, Setaria sphacellata, Braquiaria, Brachiaria humidicola.

Especies forrajeras –Fabacea:

Calopogonium, Centrosema, Desmodium, Lablab, Lotononis, Trébol pata de pájaro, Medicago arábiga, Alfalfa, Trébol caracol,  Trébol barril, Kudzú tropical, Estilosantes, Trébol de Alejandría, Trébol frutilla, Trébol encarnado, Trébol rojo, Trébol blanco, Trébol persa, Trébol subterráneo, Vicia.

Cultivos industriales:

Algodón (polinización abierta), Algodón (híbrido), Ricino,

Hortalizas:

Ocra, Cebolla (polinización abierta), Cebolla (híbrida), Apio, Acelga, Remolacha de mesa, Coliflor (polinización abierta), Coliflor (híbrida), Repollo (polinización abierta), Repollo (híbrido), Repollo chino, Nabo, Pimiento y chile (polinización abierta), Sandía (polinización abierta), Sandía (híbrida), Melón (polinización abierta), Melón (híbrido), Pepino (polinización abierta), Pepino (híbrido), Calabaza, zapallo (polinización abierta), Calabaza, zapallo (híbridos), Zanahoria, Lechuga, Calabaza de cuello (polinización abierta), Calabaza de cuello (híbrida), Tomate (polinización abierta), Tomate (híbrido), Cundeamor (polinización abierta), Perejil, Rábano, Berenjena, Espinaca (híbrida), Espinaca (polinización abierta), Espinaca de Nueva Zelandia.

ANNEX 8.

Preliminary proposal of standards for seed production of native potato varieties under the Quality Declared Seed System format

(Spanish version)

- Instalaciones y equipos Recomendados

Depósito: ambiente con un sistema de ventilación que permita la circulación de aire y preserve humedad ambiental del 60 al 70 % en el interior.

Clasificadora de semilla de papas con zarandas adaptadas para las formas alargadas y redondas de las variedades nativas de papa.

Equipo de pesado y embolsado.

Equipo de tratamiento de semillas: Fumigadoras y toldos para la aireación y secado de la semilla.

- Registro colectivo (Grupo, asociación, cooperativa o agricultores) o  individual de agricultores semilleristas e inspección cruzada

La Asociación o grupo de productores debe registrarse en la instancia pública competente que constituye el INIAF como grupo semillerista con un aval de la comunidad y el municipio que exprese un reconocimiento del potencial de la zona por su aptitud para la producción de semilla. La ficha de registro debe indicar la comunidad o comunidades y un listado de los agricultores semilleristas que componen la agrupación o asociación. El proceso de producción de semilla al interior del grupo estará basado en un sistema de control interno cruzado que se reglamentará de manera participativa.

El grupo o asociación debe estar organizado con una directiva y dos comisiones. La primera comisión está conformada por los supervisores de la inspección de campo y la segunda comisión para la comercialización de semilla.

La comisión de semilla estará a cargo de realizar las inspecciones de campo entre los 60 y 100 días después de la siembra de las parcelas inscritas en el Sistema de semilla de calidad declarada, generando reportes del estado sanitario y productivo. Esta comisión recibirá capacitación específica sobre la calidad y normativa de la producción de semilla, acreditado por un certificado emitido por la autoridad pública competente y el gobierno municipal. Se realizará la inspección cruzada de las parcelas, es decir el inspector no podrá realizar la inspección de su propia parcela.

La comisión de promoción y comercialización se encargará de valorar la información de la oferta de semilla del grupo y promoverá su comercialización realizando propaganda, participando en ferias y otras instancias de promoción y venta como la participación en ruegas de negocio entre otros.

El grupo deberá también registrar el listado de variedades de las cuales pretende producir o multiplicar semilla. El listado debe estar acompañado de la siguiente información adjunta:

2. 1. El nombre de la variedad.

2.2. Para las variedades locales:

a) una declaración del origen de la variedad;

b) una descripción simple de sus características morfológicas y de su valor para el cultivo y uso, así como indicaciones de la zona agroecológica apropiada para la variedad;

c) una declaración indicando los procedimientos a seguir para el mantenimiento de la variedad.

2.3  Para las variedades obtenidas por métodos de mejoramiento participativo:

a) declaración indicando el origen de la variedad

b) los datos obtenidos por el agricultor durante el proceso de evaluación

c) descripción de las principales características que distinguen la variedad de otras variedades.

d) declaración definiendo las zonas agroecológicas adecuadas para el cultivo de la variedad

e) declaración indicando los procedimientos a seguir para el mantenimiento de la variedad.

Las autoridades podrán requerir al solicitante muestras de semillas de un tamaño especificado para usarlas como muestras estándar de la variedad en pruebas de autenticidad que puedan ser necesarias en relación con las Semillas de Calidad Declarada.

Las autoridades deberán convenir los procedimientos requeridos para el mantenimiento de la variedad siguiendo las propuestas hechas en los párrafos anteriores.

- Requisitos de los terrenos

Utilizar preferentemente terrenos en las alturas (más de 3600 msnm) para la producción de semilla donde existe aún disponibilidad de terrenos “puruma” o terrenos “Qallpa” con más de cinco años de descanso. En las zonas altas no se encuentran muchos áfidos, vectores de los virus (PLRV y PVY) más dañinos para el cultivo. Por lo  tanto, la tasa de degeneración de la semilla de papa es más lenta. Consecuentemente, en estas zonas los agricultores pueden multiplicar sus propias semillas con menos pérdida de calidad y rendimiento (Scheidegger et al. 1989, p.6).

Los terrenos deben ser identificados con un código ligada a una ficha de registro donde se indica el nombre del propietario, la comunidad, el grupo de agricultores semilleristas al que pertenece, la superficie, la pendiente y la historia de la parcela sobre los cultivos anteriores de al menos tres años anteriores y notas relevantes sobre plagas y enfermedades que se observaron en años anteriores informado por el propietario.

3.1 Bioensayos para nematodos y verruga

Esta práctica es recomendable especialmente en terrenos “Qallpa” que han descansado menos de cinco años. No es necesario realizar los bioensayos en terrenos “puruma”. Los bioensayos consisten en colectar tierra de la parcela realizar un muestreo y en ella sembrar papa sana prebásica y poner en observación durante un mes.

4. Normas de campo

4.1 Aislamiento

La papa siendo un cultivo de propagación vegetativa no requiere en términos estrictos un aislamiento de las parcelas por razones de conservar la pureza genética sino por razones de sanidad. La existencia de parcelas aledañas con presencia marcada de virus o tizón puede afectar la sanidad de las parcelas y los rendimientos. El campo de producción de semillas deberá estar aislado de otros campos de papa por una distancia mínima de 50 m o contar con barreras vegetales como cultivos de contorno de especies diferentes como el tarwi, la quinua, avena, u otro.

4.2 Pureza varietal

La parcela debe estar correctamente identificada con el nombre de la variedad y al menos 90 % de las plantas presentes en la misma corresponden a las características de la variedad.

4.3 Malezas (general)

El campo de producción de semilla de papa deberá estar razonablemente libre de malezas; razonablemente libre significa que el crecimiento de las malezas no deberá ser tal como para impedir una evaluación correcta de las plantas.

  - Enfermedades trasmitidas por las semillas

Especial atención debe recibir la presencia de marchitez bacteriana (Ralstonia solanacearum), Verruga (Sinchytrium endobioticum), Carbón (Thecaphora solani)  y el nematodo del nódulo (Meloidogyne incognita).

Considerando las condiciones agroclimáticas de las alturas recomendadas para la producción de semilla de papa (mayor a 3600 msnm), la marchitez bacteriana tiene poca probabilidades de presentarse. Sin embargo, es necesario establecer límites para la verruga y el nematodo del nódulo.

4.5 Otras enfermedades

El campo de producción de semillas deberá estar razonablemente libre de otras enfermedades; razonablemente libre significa que la cantidad de enfermedades no debería ser tal como para impedir una evaluación correcta de las características varietales. Deben ser  tizón tardío y alternaría son frecuentes y deben ser controlados para evitar la difusión por semilla.

5.  Inspecciones cruzadas de campo

5.1 Número y época

Los campos de producción de semilla deberán ser inspeccionados por lo menos dos veces: la primera vez cuando haya cerca del 50 por ciento de floración para controlar la sanidad de las plantas y el aislamiento. La segunda vez durante la fase de maduración a la cosecha para determinar la incidencia de las enfermedades trasmitidas por las semillas y verificar las características varietales. Podrán ser necesarias inspecciones adicionales si se presentaran problemas particulares. Los inspectores deberán generar reportes de las parcelas inspeccionadas para entregar a la autoridad competente.

5.2 Técnica

4.2.1 Antes de entrar en el campo: el inspector deberá confirmar con el productor de semilla la ubicación exacta del campo, la variedad y el cultivo anterior del campo mediante la ficha de historia de la parcela.

5.2.1 En el campo

- el inspector controlará que las plantas de papa se ajusten a las características de la variedad.

- A continuación se hará una supervisión general del campo y se hará una estimación de las plantas de malezas presentes y la situación de las enfermedades. Durante esta supervisión el inspector examinará cuidadosamente 60 plantas tomadas al azar en 6 lugares separados del campo. Si el número de plantas enfermas supera el 20 %, el campo deberá ser rechazado.

5.2.2 Reporte de la inspección cruzada.

Después de la inspección, se deberá elaborar un informe aceptando o rechazando el cultivo para la producción de semilla, o recomendando medidas correctivas antes de tomar una decisión final.

- Normas de calidad de tubérculos-semillas.

Las semillas deberán ajustarse a las condiciones siguientes:

- Características morfológicas: 98 % de los tubérculos-semillas corresponden a las descritas en la ficha de la variedad registrada.

- Tamaño de semilla:

  - Primera

  - Segunda

  - tercera

- Ojos:

- Brotes:

- Sanidad:

- Etiqueta: Por desarrollar…

National Seed Authorities in previous years had indicated that the registration of native varieties had no cost, however the current authorities were not informed.

Human capital represents the skills, knowledge, work skills and good health that together enable people engage in different strategies and achieve its objectives. Social capital refers to the social resources that people have to search for the achievement of its objectives (networks and connections, participation in more formalized groups, relationships of trust, reciprocity and exchanges). Natural capital is made up of natural resources and resource flows and services from them. Physical capital comprises the basic infrastructure and productive assets. Financial capital refers to financial resources that populations used to achieve their goals.